## Compiled
Project Number | Project Title | Project Status | Financial Year | Contractor Name | Estimated Cost | Department | Implemented By | Partner | Expected Start Date | Expected End Date | Approval/Contract Number | Contract Period (Days) | Technical Rating | Completion Level | Amount Paid | Total Percentage | Project Scope | Administrative Level | Project Location | Location Names | Latitude | Longitude | ID (Source of Funds) | Funded By (Source of Funds) | Percentage of Funding (Source of Funds) | Partner (Source of Funds) | ID (Administrative Areas) | Admin (Administrative Areas) | Admin Level (Administrative Areas)
006/133/01/24-25 | Ngerenyi High altitude training centre | Complete | 2024-2025 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Ngerenyi High altitude training centre | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/02/24-25 | PIPING OF JOSA MDAMBOGHO WATER PROJECT | Complete | 2024-2025 | WAMTECH CIVIL ENGINEERING COMPANY LTD | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1992500 | 100 | PIPING OF JOSA MDAMBOGHO WATER PROJECT | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/03/24-25 | SUPPLY OF TANKS | Complete | 2024-2025 | LANCE DESIGNS LIMITED | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 998610 | 100 | SUPPLY OF TANKS | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/04/24-25 | CONSTRUCTION OF ECD MWANDISHA PRIMARY SCHOOL | Ongoing | 2024-2025 | STRNTIUM TECHNOLOGIES LIMITED | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1499508 | 100 | CONSTRUCTION OF ECD MWANDISHA PRIMARY SCHOOL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/05/24-25 | MWATUNGE FIGHINYI VIA KIZIMA ROAD GABION | Ongoing | 2024-2025 | STRNTIUM TECHNOLOGIES LIMITED | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999700 | 100 | MWATUNGE FIGHINYI VIA KIZIMA ROAD GABION | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/06/24-25 | CONSTRUCTION OF MAJENGO-SINGILA ROAD AND | Complete | 2024-2025 | DARMSTAD SYSTEMS LIMITED | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999700 | 100 | CONSTRUCTION OF MAJENGO-SINGILA ROAD AND | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/07/24-25 | YOUTH, WOMEN & PWDS EMPOWERMENT | Complete | 2024-2025 | JIENGA INVESTMENTS LTD P.O BOX 92415-80100 MOMBASA | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1998600 | 100 | YOUTH, WOMEN & PWDS EMPOWERMENT | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/08/24-25 | COMPLETION OF MLAMBENYI SOCIAL HALL | Stalled | 2024-2025 | FAXTECH COMPANY LIMITED P O BOX 495 -90300 MAKUENI | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | COMPLETION OF MLAMBENYI SOCIAL HALL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/09/24-25 | NAVCDP Poultry Project | Stalled | 2024-2025 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 0 | 100 | NAVCDP Poultry Project | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/10/24-25 | JOSA MODAMBOGHO WATER PROJECT | Complete | 2024-2025 | EKASE ENGINEERING WORKS LIMITED | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 2348768 | 100 | JOSA MODAMBOGHO WATER PROJECT | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/11/24-25 | PROPOSED CONSTRUCTION OF LANDI SOCIAL HALL IN MWATATE WARD | Complete | 2024-2025 | SENIDO ENTERPRISES LTD | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1999039.6 | 100 | PROPOSED CONSTRUCTION OF LANDI SOCIAL HALL IN MWATATE WARD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/12/24-25 | SUPPLY AND DELIVERY OF EMPOWERMENT ITEMS FOR MWATATE WARD | Complete | 2024-2025 | JIENGA INVESTMENT LIMITED | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 2494000 | 100 | SUPPLY AND DELIVERY OF EMPOWERMENT ITEMS FOR MWATATE WARD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/13/24-25 | Cabro fixing at soko ya zamani msengenyi road | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Cabro fixing at soko ya zamani msengenyi road |  |  |  | -3.4993 | 38.3766 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/14/24-25 | INSTALLATION OF STREETLIGHT AT MWAKITAU | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | INSTALLATION OF STREETLIGHT AT MWAKITAU |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/15/24-25 | KIGHALA ZARE ROAD(Formation) | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1100000 | 100 | Formation and levelling,grading |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/16/24-25 | KITUMA ROAD | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1300000 | 100 | Grading,murraming and culvert |  |  |  | -3.5005 | 38.3169 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/17/24-25 | MDODONYI MWASANGE ROAD | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Formation and grading |  |  |  | -3.4367 | 38.322 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/18/24-25 | Mwasinenyi Cooling Plant | Stalled | 2024-2025 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 800000 | 100 | Construction of Mwasinenyi Cooling Plant | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/19/24-25 | Excation of Mwasange Mdondonyi Road | Complete | 2024-2025 | White Diamond Solutions Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999900 | 100 | Construction of Excation of Mwasange Mdondonyi Road | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/20/24-25 | Excavation of Kilungu Road | Ongoing | 2024-2025 | Avator Network Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1235423 | 100 | Excavation of Kilungu Road | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/21/24-25 | Heavy Grading of Kwa Mnengwa Mwakitau Road | Ongoing | 2024-2025 | Kavuoni Construction Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 9999950 | 100 | Heavy Grading of Kwa Mnengwa Mwakitau Road | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/22/24-25 | Heavy Grading and Culverts Kituma Road | Ongoing | 2024-2025 | Fabema Enterprise Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1399900 | 100 | Heavy Grading and Culverts Kituma Road | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/23/24-25 | Formation Mwakidasi Road PH II | Complete | 2024-2025 | Idha Enterprises Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2699900 | 100 | Formation Mwakidasi Road PH II | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/24/24-25 | Fuel for Road maintenance in Bura Ward | Complete | 2024-2025 | Tsavo AutoPoint | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1300000 | 100 | Fuel for Road maintenance in Bura Ward | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/25/24-25 | Formation of Mwakuzama Road PH II | Complete | 2024-2025 | Dauval Investment | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 990489.2 | 100 | Formation of Mwakuzama Road PH II | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/26/24-25 | Formation of Mbagha Road PH II | Complete | 2024-2025 | Idha Enterprises Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 498231.6 | 100 | Formation of Mbagha Road PH II | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/27/24-25 | Formation Kighala Road | Ongoing | 2024-2025 | Joyseo Enterprises | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999900 | 100 | Formation Kighala Road | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/28/24-25 | Drilling and Developing of Gandia Kiriwenyi Borehole | Stalled | 2024-2025 | Swaham Investment Limited | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 7302026 | 100 | Drilling and Developing of Gandia Kiriwenyi Borehole | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/29/24-25 | Supply and Delivery of Tents for Bura Wards | Complete | 2024-2025 | Grincom Innovate Limited | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 2000000 | 100 | Supply and Delivery of Tents for Bura Wards | [6 empty] | County Government | 100 |  |  | Bura | Admin 3
006/133/30/24-25 | Grading and Murraming of kitivo road | Stalled | 2024-2025 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Grading and Murraming of kitivo road | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/31/24-25 | Grading and Murraming of Zare kongoronyi road | Stalled | 2024-2025 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Grading and Murraming of Zare kongoronyi road |  |  |  | -3.5107 | 38.2551 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/32/24-25 | grading and murraming of mngama-kwakele-chungaunga | Stalled | 2024-2025 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | grading and murraming of mngama-kwakele-chungaunga | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/33/24-25 | Culvert, slabbing and murraming of zare-mkuyuniroad and kongorini maribongonyi road | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Culvert, slabbing and murraming of zare-mkuyuniroad and kongorini maribongonyi road |  |  |  | -3.5105 | 38.372 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/34/24-25 | PURCHASE,PIPE FITTING BASE SETTING OF 9 10,000 LTRS PLASTIC WATER TANK | Complete | 2024-2025 | JAMALULEYL GENERAL CONTRACTOR AND SUPPLIES LIMITED | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1971386.8 | 100 | PURCHASE,PIPE FITTING BASE SETTING OF 9 10,000 LTRS PLASTIC WATER TANK | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/35/24-25 | SUPPLY AND DELIVERY OF EMPOWERNMENT ITEMS FOR CHAWIA WARD | Complete | 2024-2025 | REN DIGITAL VENTURES | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1955000 | 100 | SUPPLY AND DELIVERY OF EMPOWERNMENT ITEMS FOR CHAWIA WARD | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/36/24-25 | PROPOSED CONSTRUCTION OF KITIVO SOCIAL HALL PHASE II | Ongoing | 2024-2025 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 999990 | 100 | PROPOSED CONSTRUCTION OF KITIVO SOCIAL HALL PHASE II | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/37/24-25 | Completion of Manoa Dispensary Laboratory block | Complete | 2024-2025 | n/a | 0 | Trade, Tourism, Culture and Industrialization | County Government | [7 empty] | 0 | 100 | Completion of Manoa Dispensary Laboratory block |  |  |  | -3.5949 | 38.3326 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/38/24-25 | Renovation of manoa Dispensary | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Renovation of manoa Dispensary |  |  |  | -3.5949 | 38.3326 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/39/24-25 | Construction of Mwakinyungu toilet and tank | Complete | 2024-2025 | LERNAX AGENCIES | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of Mwakinyungu toilet and tank |  |  |  | -3.4265578 | 38.4234 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/40/24-25 | Refurbishment of Mwambirwa health centre | Complete | 2024-2025 | CROSSLAND CONSTRUCTION LIMITED | 0 | Health Services | County Government | [7 empty] | 996216.61 | 100 | Refurbishment of Mwambirwa health centre |  |  |  | -3.52880 | 38.4218 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/41/24-25 | construction of bridge kwa tole mwanyalo road murraming | Complete | 2024-2025 | Centgold Enterprises Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1999975 | 100 | Construction Of Bridge Kwa Tole Mwanyalo Road Murraming |  |  |  | -3.422784 | 38.3434 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/42/24-25 | Constuction of kidimo bridge phase 2 | Complete | 2024-2025 | Kedu Solutions | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2977919.52 | 100 | Construction Of Kidimo Bridge Phase 2 |  |  |  | -3.448939 | 38.3633 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/43/24-25 | Grading of Kishamba Chongonyi Road | Stalled | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 290000 | 100 | Grading Of Kishamba Chongonyi Road |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/44/24-25 | grading of dembwa kikoro road | Stalled | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 3000000 | 100 | Grading Of Dembwa Kikoro Road |  |  |  | -3.448939 | 38.3633 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/45/24-25 | Grading of Mwangoji Mwambingu kibaoni road | Stalled | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Grading Of Mwangoji Mwambingu Kibaoni Road |  |  |  | -3.435250 | 38.3414 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/46/24-25 | Construction Of Nguwa Water Tank | Stalled | 2024-2025 | Artic Works Limited | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 6000000 | 100 | Construction Of Nguwa Water Tank | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/47/24-25 | Equipping Of Ecdes with Indoor Equipment | Complete | 2024-2025 | Katemony International Ltd | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 2494999.92 | 100 | Equipping Of Ecdes with Indoor Equipment | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/48/24-25 | Pipping Of Mombasa Shop Mwakuni Water Project | Ongoing | 2024-2025 | Tifant Ventures Limited | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1999984 | 100 | Pipping Of Mombasa Shop Mwakuni Water Project | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/49/24-25 | Construction Of Nguwa Kighala-Kirughunyi Water Project | Ongoing | 2024-2025 | Yoani Ventures Limited | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1847500 | 100 | Construction Of Nguwa Kighala-Kirughunyi Water Project | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/50/23-24 | PIPING OF JOSA MDAMBOGHO WATER PROJECT | Complete | 2023-2024 | WAMTECH CIVIL ENGINEERING COMPANY LTD | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1992500 | 100 | PIPING OF JOSA MDAMBOGHO WATER PROJECT | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/51/23-24 | SUPPLY OF TANKS | Complete | 2023-2024 | LANCE DESIGNS LIMITED | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 998610 | 100 | SUPPLY OF TANKS | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/52/23-24 | CONSTRUCTION OF ECD MWANDISHA PRIMARY SCHOOL | Complete | 2023-2024 | STRNTIUM TECHNOLOGIES LIMITED | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1499508 | 100 | CONSTRUCTION OF ECD MWANDISHA PRIMARY SCHOOL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/53/23-24 | MWATUNGE FIGHINYI VIA KIZIMA ROAD GABION | Ongoing | 2023-2024 | STRNTIUM TECHNOLOGIES LIMITED | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999700 | 100 | MWATUNGE FIGHINYI VIA KIZIMA ROAD GABION | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/54/23-24 | CONSTRUCTION OF MAJENGO-SINGILA ROAD AND | Complete | 2023-2024 | DARMSTAD SYSTEMS LIMITED | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999700 | 100 | CONSTRUCTION OF MAJENGO-SINGILA ROAD AND | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/55/23-24 | YOUTH, WOMEN & PWDS EMPOWERMENT | Complete | 2023-2024 | JIENGA INVESTMENTS LTD P.O BOX 92415-80100 MOMBASA | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1998600 | 100 | YOUTH, WOMEN & PWDS EMPOWERMENT | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/56/23-24 | COMPLETION OF MLAMBENYI SOCIAL HALL | Complete | 2023-2024 | FAXTECH COMPANY LIMITED P O BOX 495 -90300 MAKUENI | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | COMPLETION OF MLAMBENYI SOCIAL HALL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/57/23-24 | CONSTRUCTION OF PELELEZA SOCIAL HALL 4-DOOR TOILET | stalled | 2023-2024 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 999479.2 | 100 | CONSTRUCTION OF PELELEZA SOCIAL HALL 4-DOOR TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/58/23-24 | PROPOSED CONSTRUCTION OF KIPUSI SOCAIL HALL 4 DOOR TOILET | stalled | 2023-2024 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 99279 | 100 | PROPOSED CONSTRUCTION OF KIPUSI SOCAIL HALL 4 DOOR TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/59/23-24 | Construction of landi maili kumi primary mdindinyi | Complete | 2023-2024 | n/a | 0 |  | County Government | [7 empty] | 2000000 | 100 | Construction of landi maili kumi primary mdindinyi |  |  |  | -3.4287 | 38.4468 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/60/23-24 | Construction of Bura Staff House | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2000000 | 100 | Construction of Bura Staff House |  |  |  | -3.5006 | 38.3171 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/61/23-24 | CONSTRUCTION OF KWA MNEGWA ECDE | Complete | 2023-2024 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1227000 | 100 | CONSTRUCTION OF KWA MNEGWA ECDE |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/62/23-24 | SLABBING OF MWAKUZAMA ROAD | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 3000000 | 100 | Excavation, grading and slabbing |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/63/23-24 | FORMATION OF MWAKIDASI ROAD | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 3000000 | 100 | Formation,grading and roller |  |  |  | -3.4786 | 38.3197 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/64/23-24 | PURCHASE, PIPE FITTING, BASEMENT AND SETTING OF 9 10000LITRES PLASTIC WATER TANKS | Complete | 2023-2024 | BREGZA ENTERPRISES | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1400000 | 100 | PURCHASE, PIPE FITTING, BASEMENT AND SETTING OF 9 10000LITRES PLASTIC WATER TANKS | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/65/23-24 | REHABILITATION OF ZARE WATER DISTRIBUTION LINE | Complete | 2023-2024 | MAKA INDUSTIRES LIMITED | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 999915 | 100 | REHABILITATION OF ZARE WATER DISTRIBUTION LINE | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/66/23-24 | CHAWIA ROADS | Complete | 2023-2024 | HANZ PETROLEUM | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | CHAWIA ROADS | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/67/23-24 | YOUTH WOMEN AND PLWD EMPOWERMENT | Complete | 2023-2024 | ROPEMA GENERAL ENTERPRISES LTD PO. BOX 97634-80112 MOMBASA | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1663900 | 100 | YOUTH WOMEN AND PLWD EMPOWERMENT | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/68/23-24 | CHAWIA TOURNAMENT | Complete | 2023-2024 | YANKEM IMAGES | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 508500 | 100 | CHAWIA TOURNAMENT | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/69/23-24 | COMPLETION OF KITIVO SOCIAL HALL | Ongoing | 2023-2024 | MAFAZARA ENTERPRISES P.O BOX 86612-80100 MOMBASA | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 2992553 | 100 | COMPLETION OF KITIVO SOCIAL HALL | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/70/23-24 | Completetion of Manoa Dispensary | Complete | 2023-2024 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Completetion of Manoa Dispensary |  |  |  | -3.5949 | 38.3326 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/71/23-24 | Construction of Mwakinyungu toilet and tank | Complete | 2023-2024 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 996216.61 | 100 | Construction of Mwakinyungu toilet and tank |  |  |  | -3.4265578 | 38.4234 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/72/23-24 | Refurbishment of Mwambirwa health centre | Complete | 2023-2024 | n/a | 0 | Health Services | County Government | [7 empty] | 1999975 | 100 | Refurbishment of Mwambirwa health centre |  |  |  | -3.52880 | 38.4218 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/73/23-24 | construction of Kilulunyi shongolonyi catholic vichwala | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1778923.8 | 100 | construction of Kilulunyi shongolonyi catholic vichwala |  |  |  | -3.463261 | 38.3421 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/74/23-24 | Construction of Kidimo Bridge | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2998072 | 100 | Construction of Kidimo Bridge |  |  |  | -3.448939 | 38.3633 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/75/23-24 | construction of Mlangonyi kishamba masungunyi mwachawaza road | Stalled | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 5000000 | 100 | construction of Mlangonyi kishamba masungunyi mwachawaza road |  |  |  | -3.455343 | 38.3704 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/76/23-24 | Construction Of Kidaya/Ngerenyi Water Tank in Fururu | Complete | 2023-2024 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 4583063 | 100 | Construction Of Kidaya/Ngerenyi Water Tank in Fururu | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/77/23-24 | Fuel For Grading Playgrounds and Roads | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 300000 | 100 | Fuel For Grading Playgrounds and Roads | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/78/22-23 | Maintenance of Josa Modambogo water-project | Complete | 2022-2023 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Maintenance of Josa Modambogo water-project | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/79/22-23 | Drilling of Mdindinyi - Kireti borehole | Complete | 2022-2023 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Drilling of Mdindinyi - Kireti borehole | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/80/22-23 | Development of Wards VTCs | Complete | 2022-2023 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Development of Wards VTCs | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/81/22-23 | Maintenance of Mwatate roads | Complete | 2022-2023 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Maintenance of Mwatate roads | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/82/22-23 | CONSTRUCTION OF PELELEZA SOCIAL HALL 4-DOOR TOILET | Complete | 2022-2023 | CORFA COMPANY LIMITED | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 999479.2 | 100 | CONSTRUCTION OF PELELEZA SOCIAL HALL 4-DOOR TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/83/22-23 | supply and delivery of 100 seater tents, plastic chairs which includes;100 SEATER TENTS ,PLASTIC CHAIRS | Complete | 2022-2023 | JIENGA INVESTMENTS LTD P.O BOX 92415-80102 | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1998000 | 100 | supply and delivery of 100 seater tents, plastic chairs which includes;100 SEATER TENTS ,PLASTIC CHAIRS | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/84/22-23 | PROPOSED COMPLETION OF MLAMBENYI SOCIAL HALL | Complete | 2022-2023 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | PROPOSED COMPLETION OF MLAMBENYI SOCIAL HALL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/85/22-23 | PROPOSED CONSTRUCTION OF KIPUSI SOCAIL HALL 4 DOOR TOILET | Complete | 2022-2023 | FAXTECH COMPANY LTD | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 99279 | 100 | PROPOSED CONSTRUCTION OF KIPUSI SOCAIL HALL 4 DOOR TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/86/22-23 | MAINTANANCE OF MWATATE ROADS | Complete | 2022-2023 | BLUE AVENUE VENTURES | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2000000 | 100 | MAINTANANCE OF MWATATE ROADS | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/87/22-23 | DRIVING SCHOOL FOR 66 STUDENTS | Complete | 2022-2023 | TRUNK DRIVING SCHOOL | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1635000 | 100 | DRIVING SCHOOL FOR 66 STUDENTS | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/88/22-23 | CONSTRUCTION OF PELELEZA SOCIAL HALL 4-DOOR TOILET | stalled | 2022-2023 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 999479.2 | 100 | CONSTRUCTION OF PELELEZA SOCIAL HALL 4-DOOR TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/89/22-23 | PROPOSED CONSTRUCTION OF KIPUSI SOCAIL HALL 4 DOOR TOILET | stalled | 2022-2023 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 99279 | 100 | PROPOSED CONSTRUCTION OF KIPUSI SOCAIL HALL 4 DOOR TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/90/22-23 | MWAMKOLO ROAD | Complete | 2022-2023 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Formation, filling and roller |  |  |  | -3.5001 | 38.3176 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/91/22-23 | CONSTRUCTION OF MAKANGA SOCIAL HALL 2 DOOR TOILET | Complete | 2022-2023 | ROMWAKI ENTERPRISES (E.A ) LTD 17 NG'AMBWA | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 800000 | 100 | CONSTRUCTION OF MAKANGA SOCIAL HALL 2 DOOR TOILET | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/92/22-23 | PROPOSED CONSTRUCTION OF KITIVO SOCIAL HALL | Complete | 2022-2023 | KIZU ENTERPRISES LTD P.O BOX 107 NG'AMBWA | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 2999905 | 100 | PROPOSED CONSTRUCTION OF KITIVO SOCIAL HALL | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/93/22-23 | SUPPLY AND DELIVERY OF SPORT ITEMS AND OTHER ASSORTED ITEMS | Complete | 2022-2023 | PATIKINA ENTERPRISES P.O BOX 68-80305 MWATATE | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1000000 | 100 | SUPPLY AND DELIVERY OF SPORT ITEMS AND OTHER ASSORTED ITEMS | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/94/22-23 | DRIVING SCHOOL TRAINING FOR 43 STUDENTS | Complete | 2022-2023 | TRUCK DRIVING SCHOOL | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1635000 | 100 | DRIVING SCHOOL TRAINING FOR 43 STUDENTS | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/95/22-23 | COMPLETION OF MANOA DISPENSARY LABORATORY | Complete | 2022-2023 | DISTON INVESTMENT LIMITED | 0 | Health Services | County Government | [7 empty] | 3105508 | 100 | COMPLETION OF MANOA DISPENSARY LABORATORY |  |  |  | -3.5949 | 38.3326 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/96/22-23 | SUPPLY AND DELIVERY OF PLASTIC TANKS | Complete | 2022-2023 | FEDHA KENYA LIMITED | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 999920 | 100 | SUPPLY AND DELIVERY OF PLASTIC TANKS | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/97/22-23 | REHABILITATION OF ALIA WATER PROJECT | Complete | 2022-2023 | SCAN CONSTRUCTION LIMITED | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 2992800 | 100 | REHABILITATION OF ALIA WATER PROJECT | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/98/22-23 | MAINTANANCE OF CHAWIA ROADS | Complete | 2022-2023 | MWANEDU GENERAL HOLDINGS | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2000000 | 100 | MAINTANANCE OF CHAWIA ROADS | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/99/22-23 | BUSH CLEARING OF CHAWIA ROADS | Complete | 2022-2023 | LIANTO CONTRACTORS LIMITED | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 498496 | 100 | BUSH CLEARING OF CHAWIA ROADS | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/100/22-23 | Alia Borehole | Complete | 2022-2023 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Alia Borehole |  |  |  | -3.4806 | 38.2696 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/101/22-23 | Kirongwe Road Rehabillitation | Complete | 2022-2023 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Kirongwe Road Rehabillitation |  |  |  | -3.5164 | 38.372 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/102/22-23 | Shelemba Dispensary Renovations | Complete | 2022-2023 | n/a | 0 | Health Services | County Government | [7 empty] | 2500000 | 100 | Shelemba Dispensary Renovations |  |  |  | -3.433981 | 38.4705 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/103/22-23 | Mshokore Kidaya Ifumbu Road | Complete | 2022-2023 | Rare Eagle Investment Ltd | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 4875732.88 | 100 | Mshokore Kidaya Ifumbu Road |  |  |  | -3.450648 | 38.3543 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/104/22-23 | Mwambisi Dam | Complete | 2022-2023 | Beachroad Hauliers Limited | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 2897000 | 100 | Mwambisi Dam | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/105/22-23 | Kisaghala Water Project | Complete | 2022-2023 | Saleh Construction and Road Works Limited | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1162795 | 100 | Kisaghala Water Project | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/106/22-23 | Completion Of Dembwa | Complete | 2022-2023 | Vision Track Ventures Limited | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 1999997 | 100 | Completion Of Dembwa | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/107/22-23 | Training Of Community Health Workers | Complete | 2022-2023 | n/a | 0 | Health Services | County Government | [7 empty] | 800000 | 100 | Training Of Community Health Workers | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/108/22-23 | Supply And Delivery of Sport Items and Other Assorted Items | Complete | 2022-2023 | Dadima Supplies and Services P.O Box 5851-00100 Nairobi | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 700000 | 100 | Supply And Delivery of Sport Items and Other Assorted Items | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/109/22-23 | Supply And Delivery of Tents and Plastic Chairs for Wusi Kishamba | Complete | 2022-2023 | Jibtat Kenya P.O Box 41749-80100 Mombasa | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 780000 | 100 | Supply And Delivery of Tents and Plastic Chairs for Wusi Kishamba | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/110/22-23 | Supply Of Green Grams-Mpizinyi Cooperative | Complete | 2022-2023 | Mwatate Greengram Growers Investment | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 1000000 | 100 | Supply Of Green Grams-Mpizinyi Cooperative | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/111/21-22 | Supply of tree seedlings for Bidii Nguvu SHG | Complete | 2021-2022 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 0 | 100 | Supply of tree seedlings for Bidii Nguvu SHG | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/112/21-22 | 10 water tanks of 5,000 litres capacity | Complete | 2021-2022 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 0 | 100 | 11 water tanks of 5,000 litres capacity | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/113/21-22 | Grading, levelling and installation of goalposts of Mwatate Primary School | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 200000 | 100 | Grading, levelling and installation of goalposts of Mwatate Primary School |  |  |  | -3.5032 | 38.374 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/114/21-22 | Grading, levelling and installation of goalposts of Mwandala Primary School | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 200000 | 100 | Grading, levelling and installation of goalposts of Mwandala Primary School | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/115/21-22 | Msikitini ECDE center | Complete | 2021-2022 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Msikitini ECDE center | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/116/21-22 | development of VTCs | Complete | 2021-2022 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | development of VTCs | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/117/21-22 | murraming and culverting of Mwatunge- Catholic Church | Stalled | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | murraming and culverting of Mwatunge- Catholic Church |  |  |  | -3.4969 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/118/21-22 | Sunrise Academy - Soko ya Zamani Petrol Station | Stalled | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | Sunrise Academy - Soko ya Zamani Petrol Station |  |  |  | -3.4949 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/119/21-22 | Murraming of Kidulonyi - Msisinenyi Road | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Murraming of Kidulonyi - Msisinenyi Road |  |  |  | -3.48 | 38.3832 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/120/21-22 | Madungunyi - Hill Slopes Road | Stalled | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | Madungunyi - Hill Slopes Road |  |  |  | -3.4949 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/121/21-22 | Kiwetonyi adjudication exercise | Complete | 2021-2022 | n/a | 0 | Lands, Physical Planning, Mining and Urban Development | County Government | [7 empty] | 0 | 100 | Kiwetonyi adjudication exercise | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/122/21-22 | Completion of Singila-Majengo adjudication exercise | Complete | 2021-2022 | n/a | 0 | Lands, Physical Planning, Mining and Urban Development | County Government | [7 empty] | 0 | 100 | Completion of Singila-Majengo adjudication exercise | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/123/21-22 | Darts center | Complete | 2021-2022 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Darts center | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/124/21-22 | Sports activities | Complete | 2021-2022 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Sports activities | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/125/21-22 | 600 chairs | Complete | 2021-2022 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | 601 chairs | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/126/21-22 | full Public Address systems | Complete | 2021-2022 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | full Public Address systems | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/127/21-22 | Construction of Mwakitau ECDE | Complete | 2021-2022 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1400000 | 100 | CONSTRUCTION OF MWAKITAU ECDE |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/128/21-22 | Mnamu VTC Refurbishment | Complete | 2021-2022 | n/a | 0 |  | County Government | [7 empty] | 1500000 | 100 | Mnamu VTC Refurbishment |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/129/21-22 | TUNGULU KWA WENI MWANGI ROAD | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Grading and culvert |  |  |  | -3.4367 | 38.2201 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/130/21-22 | Complition of Mengo dispensary toilet | Complete | 2021-2022 | n/a | 0 | Health Services | County Government | [7 empty] | 400000 | 100 | Complition of Mengo dispensary toilet |  |  |  | -3.436802 | 38.4737 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/131/21-22 | Kidaya ifumbu Road Murraming | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 750000 | 100 | murraming road of Kidaya Ifumbu |  |  |  | -3.450648 | 38.3543 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/132/21-22 | mbengonyi chongonyi road | Stalled | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | mbengonyi chongonyi road |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/133/21-22 | Cheleka kishamba road | Stalled | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Cheleka kishamba road |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/134/21-22 | completion of Josa & dembwa Playing fields | Stalled | 2021-2022 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1500000 | 100 | completion of Josa & dembwa Playing fields |  |  |  | -3.448939 | 38.3633 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/135/20-21 | MAJENGO ECD AND TOILET | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | MAJENGO ECD AND TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/136/20-21 | COMPLETION OF MWATUNGE LIBRARY | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | COMPLETION OF MWATUNGE LIBRARY | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/137/20-21 | JUNIOUR ACADEMY LANDI - MDINDINYI ROAD | Stalled | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1200600 | 100 | JUNIOUR ACADEMY LANDI - MDINDINYI ROAD |  |  |  | -3.4287 | 38.4468 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/138/20-21 | REHABILITATION OF MWATATE FEEDER ROADS | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | REHABILITATION OF MWATATE FEEDER ROADS | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/139/20-21 | FUEL FOR MWATATE ROADS | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | FUEL FOR MWATATE ROADS | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/140/20-21 | Kiwetonyi(Mwatunge)Adjudication | Complete | 2020-2021 | n/a | 0 | Lands, Physical Planning, Mining and Urban Development | County Government | [7 empty] | 0 | 100 | Kiwetonyi(Mwatunge)Adjudication | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/141/20-21 | TENTS 10 PIECES | Complete | 2020-2021 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | TENTS 10 PIECES | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/142/20-21 | YOUTH, WOMEN AND PWD'S EMPOWERMENT | Complete | 2020-2021 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | YOUTH, WOMEN AND PWD'S EMPOWERMENT | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/143/20-21 | 16 MOTOR CYCLES | Complete | 2020-2021 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | 17 MOTOR CYCLES | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/144/20-21 | PELELEZA SOCIAL HALL AND TOILET | Complete | 2020-2021 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | PELELEZA SOCIAL HALL AND TOILET | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/145/20-21 | COMPLETION OF MLAMBENYI SOCIAL HALL | Complete | 2020-2021 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | COMPLETION OF MLAMBENYI SOCIAL HALL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/146/20-21 | COMPLETION OF LANDI SOCIAL HALL | Complete | 2020-2021 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | COMPLETION OF LANDI SOCIAL HALL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/147/20-21 | COMPLETION OF KIPUSI SOCIAL HALL | Complete | 2020-2021 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | COMPLETION OF KIPUSI SOCIAL HALL | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/148/20-21 | CONSTRUCTION OF KWA MNEGWA ECDE | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1227000 | 100 | CONSTRUCTION OF KWA MNEGWA ECDE |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/149/20-21 | construction of mwashuma dispensary | stalled | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 2000000 | 100 | construction of mwashuma dispensary |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/150/20-21 | Proposed rehabilitation of Iribongonyi sechu Road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 598792 | 100 | Proposed rehabilitation of Iribongonyi sechu Road | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/151/20-21 | Proposed slabbing of Jonathan Mwakio Road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 522255 | 100 | Proposed slabbing of Jonathan Mwakio Road | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/152/20-21 | Proposed slabbing of Kironge mazola Road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1296237 | 100 | Proposed slabbing of Kironge mazola Road | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/153/20-21 | Proposed expansion of Mwamkolo road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1100000 | 100 | Proposed expansion of Mwamkolo road | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/154/20-21 | Proposed slabbing of Mwatalu kirughurunyi | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1674170 | 100 | Proposed slabbing of Mwatalu kirughurunyi | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/155/20-21 | Completion of Kamtonga Dispensary - Waiting bay,staff and patient toilet, renovation of the container | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 3616060 | 100 | Completion of Kamtonga Dispensary - Waiting bay,staff and patient toilet, renovation of the container | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/156/20-21 | Equipping of Chawia Dispensary | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 2997000 | 100 | Equipping of Chawia Dispensary | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/157/20-21 | CONSTRUCTION OF A LABORATORY BLOCK AT MANOA DISPENSARY | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 3105508.2 | 100 | CONSTRUCTION OF A LABORATORY BLOCK AT MANOA DISPENSARY | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/158/20-21 | Construction of Delivery room Manoa Dispensary - Sup | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 2999522 | 100 | Construction of Delivery room Manoa Dispensary - Sup | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/159/20-21 | RENOVATION OF MANOA DISPENSARY | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 1228971.3 | 100 | RENOVATION OF MANOA DISPENSARY | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/160/20-21 | Proposed rehabilitation of Baghau road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 5690330 | 100 | Proposed rehabilitation of Baghau road | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/161/20-21 | Proposed slabbing of Mwakaleri Road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 4218684 | 100 | Proposed slabbing of Mwakaleri Road | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/162/20-21 | Construction of Mengo Dispensary | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 4995970 | 100 | Consrtuction of Mengo Dispensary | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/163/20-21 | Construction of Baghau dispensary | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 4756420 | 100 | Construction of Baghau dispensary | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/164/20-21 | Kilulunyi Vichwala road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Kilulunyi Vichwala road |  |  |  | -3.463261 | 38.3421 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/165/20-21 | Kilulunyi Vichwala road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | Kilulunyi Vichwala road |  |  |  | -3.557919 | 38.8458 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/166/20-21 | Kidimo road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | Kidimo road |  |  |  | -3.448939 | 38.3633 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/167/20-21 | kidaya kisaghala ngerenyi road murraming | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | murraming road of Kidaya Kisaghala ngerenyi |  |  |  | -3.435250 | 38.3414 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/168/20-21 | mbengonyi chongonyi road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | mbengonyi chongonyi road |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/169/19-20 | Routine maintenace and spot improvement | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Routine maintenace and spot improvement | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/170/19-20 | Gandia Mwatunge Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Gandia Mwatunge Road | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/171/19-20 | Kariobangi SDA Church Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Kariobangi SDA Church Road | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/172/19-20 | Women REP Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Women REP Road | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/173/19-20 | Kamtonga-Dighai-Chunga unga-Manoa (Culverting & Murraming) | Complete | 2019-2020 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Kamtonga-Dighai-Chunga unga-Manoa (Culverting & Murraming) |  |  |  | -3.6152 | 38.3094 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/174/19-20 | mbilimbi Footbridge | Complete | 2019-2020 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | mbilimbi Footbridge | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/175/19-20 | Completion of Kamtonga Dispensary | Complete | 2019-2020 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Completion of Kamtonga Dispensary |  |  |  | -3.3969 | 38.5571 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/176/19-20 | Spot Improvement of Wafu Kironge Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 549321 | 100 | Spot Improvement of Wafu Kironge Road | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/177/19-20 | Upgrading of Infrastructure-Mwatate Hospital | Complete | 2019-2020 | n/a | 0 | Health Services | County Government | [7 empty] | 22400000 | 100 | Upgrading of Infrastructure-Mwatate Hospital | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/178/19-20 | maintenance of mlangonyi kishamba road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 5000000 | 100 | maintenance of mlangonyi kishamba road |  |  |  | -3.455343 | 38.3704 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/179/18-19 | Maintainance of County Street Lights | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Maintainance of County Street Lights | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/180/18-19 | disilting of ziwa la ng'ombe | Complete | 2018-2019 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | disilting of ziwa la ng'ombe |  |  |  | -3.4821 | 38.4191 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/181/18-19 | Murraming of soko mpya bridge to lerinyi bridge | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Murraming of soko mpya bridge to lerinyi bridge |  |  |  | -3.5068 | 38.3776 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/182/18-19 | construction of peleleza footbridge | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | construction of peleleza footbridge |  |  |  | -3.5057 | 38.3775 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/183/18-19 | Construction of bridge soko ya zamani jombo road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Construction of bridge soko ya zamani jombo road |  |  |  | -3.4993 | 38.3766 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/184/18-19 | Construction of madungunyi bridge | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Construction of madungunyi bridge |  |  |  | -3.4949 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/185/18-19 | Construction of Bura Social Hall | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Construction of Bura Social Hall |  |  |  | -3.5005 |  |  | County Government | 100 |  |  | Bura | Admin 3
006/133/186/18-19 | CONSTRUCTION OF MLUGHI ECDE | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | CONSTRUCTION OF MLUGHI ECDE |  |  |  | -3.5006 |  |  | County Government | 100 |  |  | Bura | Admin 3
006/133/187/18-19 | INSTALLATION OF GENERATOR | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | INSTALLATION OF GENERATOR |  |  |  | -3.5006 |  |  | County Government | 100 |  |  | Bura | Admin 3
006/133/188/18-19 | Renovation of mrughuwa Dispensary | Complete | 2018-2019 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Renovation of mrughuwa Dispensary |  |  |  | -3.5006 |  |  | County Government | 100 |  |  | Bura | Admin 3
006/133/189/18-19 | Slabbing Wumari Road | Complete | 2018-2019 | REENAH K LIMITED | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Slabbing Wumari Road |  |  |  | -3.5105 | 38.3283 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/190/18-19 | Contruction of mwambula footbridge | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Contruction of mwambula footbridge | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/191/18-19 | Spot Improvement of wafu kironge road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Spot Improvement of wafu kironge road |  |  |  | -3.4699 | 38.3451 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/192/18-19 | mruru-mwakoto-sechu rd | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | mruru-mwakoto-sechu rd |  |  |  | -3.4926 | 38.378 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/193/18-19 | Culverts at Preston Msafari(Mwandala) | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Culverts at Preston Msafari(Mwandala) | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/194/18-19 | mruru-mwakoto-sechu rd | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2035880 | 100 | mruru-mwakoto-sechu rd |  |  |  | -3.4926 | 38.378 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/195/18-19 | Maribongonyi Kirongwe Road | Complete | 2018-2019 | FULL MZUKA ENTERPRISE | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2414169 | 100 | Maribongonyi Kirongwe Road |  |  |  | -3.5164 | 38.372 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/196/18-19 | levelling of mwakitutu primary school grounds | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | levelling of mwakitutu primary school grounds |  |  |  | -3.506 | 38.3674 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/197/18-19 | construction of footbridge at sechu primary school | Complete | 2018-2019 | ABORI STORES | 0 | Health Services | County Government | [7 empty] | 0 | 100 | construction of footbridge at sechu primary school |  |  |  | -3.492 | 38.3286 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/198/18-19 | Kamtonga ECDE | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Kamtonga ECDE |  |  |  | -3.631 | 38.3661 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/199/18-19 | Construction Of Alia Ecde Toilet - Labour Based Twin Door | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction Of Alia Ecde Toilet - Labour Based Twin Door |  |  |  | -3.4806 | 38.2696 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/200/18-19 | Supply Of 10,000L Plastic Tank To Mdendenyi Borehole (Pending Bill) | Complete | 2018-2019 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Supply Of 10,000L Plastic Tank To Mdendenyi Borehole (Pending Bill) |  |  |  | -3.5164 | 38.372 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/201/18-19 | Mdeminyi Water Project | Complete | 2018-2019 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Mdeminyi Water Project |  |  |  | -3.5164 | 38.372 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/202/18-19 | Construction of Chungaunga ECD Toilet labour Based | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of Chungaunga ECD Toilet labour Based |  |  |  | -3.6038 | 38.3115 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/203/18-19 | Expansion Mruru-Mwakoto-Sechu road | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1460960 | 100 | Expansion Mruru-Mwakoto-Sechu road | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/204/18-19 | Rehab. Kironge Town - Mazola Pri, Sch Rd | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1499915 | 100 | Rehab. Kironge Town - Mazola Pri, Sch Rd | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/205/18-19 | Health Centre for Kamtonga | Complete | 2018-2019 | n/a | 0 | Health Services | County Government | [7 empty] | 1000000 | 100 | Health Centre for Kamtonga | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/206/18-19 | Construction of Dighai ECDE | Complete | 2018-2019 | GM Contractors Limited | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1398548.2 | 100 | Construction of Dighai ECDE | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/207/18-19 | Baghau road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 4431113 | 100 | Construction of baghau road | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/208/18-19 | Expansion of Kishau road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1413752 | 100 | Expansion of Kishau road | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/209/18-19 | Kishau primary ECD | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 2116379.4 | 100 | Kishau primary ECD |  |  |  | -3.379925 | 38.4345 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/210/18-19 | CONSTRUCTION OF SHELEMBA WATER PROJECT | Complete | 2018-2019 | n/a | 0 |  | County Government | [7 empty] | 392150 | 100 | CONSTRUCTION OF SHELEMBA WATER PROJECT | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/211/18-19 | Construction of kighombo boda boda shed | Complete | 2018-2019 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 728248 | 100 | Construction of kighombo boda boda shed |  |  |  | -3.382995 | 38.4546 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/212/18-19 | Construction of Mwanga ECDE | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1438690 | 100 | Construction of Mwanga ECDE |  |  |  | -3.404213 | 38.4464 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/213/18-19 | Construction 0f twin workshop Msau VTC phase 1 | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1996464.4 | 100 | Construction 0f twin workshop Msau VTC phase 1 |  |  |  | -3.416071 | 38.4108 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/214/18-19 | Kilulunyi Vichwala (Spot Murraming) | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | Spot Murraming of KIlulunyi |  |  |  | -3.463261 | 38.3421 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/215/18-19 | Murray Josa road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Murray Josa road |  |  |  | -3.430843 | 38.3599 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/216/18-19 | Bura-Mararo road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Bura-Mararo road |  |  |  | -3.458585 | 38.3397 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/217/18-19 | Rehabilitation Of chae solome road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 499100 | 100 | Rehabilitation Of chae solome road |  |  |  | -3.463261 | 38.3421 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/218/18-19 | Dembwa Mpizinyi Road Formation | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1350000 | 100 | Formation of Dembwa Mpizinyi |  |  |  | -3.4489 | 38.3633 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/219/18-19 | Murraming of Ramunyi Mlambenyi | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Murraming of Ramunyi Mlambenyi |  |  |  | -3.436376 | 38.3763 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/220/18-19 | Murraming of kilulunyi vichwala | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | Murraming of kilulunyi vichwala |  |  |  | -3.463261 | 38.3421 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/221/18-19 | Excavation of Cheleka Josa | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Excavation of Cheleka Josa |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/222/18-19 | Murraming of Mreshinyi ngerenyi | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | Murraming of Mreshinyi ngerenyi |  |  |  | -3.435250 | 38.3414 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/223/18-19 | Road maintenance josa kizingo chongonyi | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | maintenance of josa kizingo chongonyin road |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/224/18-19 | completion of rehabilitation Of kidaya and vichwala ecd playing field | Complete | 2018-2019 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1000000 | 100 | completion of rehabilitation Of kidaya and vichwala ecd playing field |  |  |  | -3.488494 | 38.322 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/225/17-18 | Mwatate ECDs water hatvesting project | Complete | 2017-2018 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Mwatate ECDs water hatvesting project | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/226/17-18 | Kariobangi water project piping - purchase of 2 water tanks & installation | Complete | 2017-2018 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Kariobangi water project piping - purchase of 2 water tanks & installation | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/227/17-18 | Mwatate water tank distribution and extension to kisima – mwatate – msisinenyi – Mazola B – mlambenyi - mzwanenyi | Complete | 2017-2018 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Mwatate water tank distribution and extension to kisima – mwatate – msisinenyi – Mazola B – mlambenyi - mzwanenyi | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/228/17-18 | Purchase and installation of 10,000 liter tanks and gutters in all the 10 mwatate ward ECDE’s | Complete | 2017-2018 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Purchase and installation of 10,000 liter tanks and gutters in all the 10 mwatate ward ECDE’s | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/229/17-18 | Construction of Kipusi ecd classroom | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of Kipusi ecd classroom | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/230/17-18 | Construction of Mzwanenyi ecd classroom | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1294826.8 | 100 | Construction of Mzwanenyi ecd classroom | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/231/17-18 | Construction of mwatate ECDE 4 door toilet- Labour based | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of mwatate ECDE 4 door toilet- Labour based | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/232/17-18 | CONSTRUCTION MSISINENYI ECD | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | CONSTRUCTION MSISINENYI ECD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/233/17-18 | CONSTRUCTION MWATUNGE ECD | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | CONSTRUCTION MWATUNGE ECD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/234/17-18 | Mwatunge ECDE playing field leveling | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 500000 | 100 | Mwatunge ECDE playing field leveling |  |  |  | -3.4983 | 38.3992 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/235/17-18 | CONSTRUCTION MWANDALA ECD | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | CONSTRUCTION MWANDALA ECD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/236/17-18 | Construction of Mlambenyi YP twin workshop block | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Construction of Mlambenyi YP twin workshop block | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/237/17-18 | MODAMBOGHO DISPENSARY (Fencing) | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | MODAMBOGHO DISPENSARY (Fencing) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/238/17-18 | YOUTH SPORTS Activities - Tournament, purchase of sports kit | Complete | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | YOUTH SPORTS Activities - Tournament, purchase of sports kit | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/239/17-18 | Construction of Mwatate town - Mwakitutu road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2000000 | 100 | Construction of Mwatate town - Mwakitutu road |  |  |  | -3.5012 | 38.3733 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/240/17-18 | Culverting of soko ya zamani-jombo road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Culverting of soko ya zamani-jombo road |  |  |  | -3.4993 | 38.3766 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/241/17-18 | culverting darius mbela foundation-mdeminyi road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | culverting darius mbela foundation-mdeminyi road |  |  |  | -3.4757 | 38.4533 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/242/17-18 | Culvert mzwanenyi-maghoro road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Culvert mzwanenyi-maghoro road |  |  |  | -3.4674 | 38.3929 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/243/17-18 | Culvert Kenyatta junction-catholic road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 600000 | 100 | Culvert Kenyatta junction-catholic road |  |  |  | -3.5032 | 38.394 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/244/17-18 | Construction of Kwa Daudi - Madungunyi Bridge | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1900000 | 100 | Construction of Kwa Daudi - Madungunyi Bridge |  |  |  | -3.4949 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/245/17-18 | Upgrade of soko ya zamani- kenyatta road (streetlights) | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Upgrade of soko ya zamani- kenyatta road (streetlights) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/246/17-18 | Construction of Peleleza Bridge and Murraming | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | Construction of Peleleza Bridge and Murraming |  |  |  | -3.5055 | 38378286 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/247/17-18 | Grading and Murraming of Peleleza Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | Grading and Murraming of Peleleza Road |  |  |  | -3.5055 | 38378286 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/248/17-18 | Driving Course for Youth - Mwatate ward | Complete | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Driving Course for Youth - Mwatate ward | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/249/17-18 | Construction of Crush Pen at Bura | Complete | 2017-2018 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 1850000 | 100 | CONSTRUCTION OF CRUSH AT BURA |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/250/17-18 | grading and murraming of kironge mazola rd | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | grading and murraming of kironge mazola rd |  |  |  | -3.4699 | 38.3451 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/251/17-18 | mwangoji mwakoto road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | mwangoji mwakoto road |  |  |  | -3.4926 | 38.378 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/252/17-18 | formation of jombo manganga mruru | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | formation of jombo manganga mruru |  |  |  | -3.5036 | 38.3751 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/253/17-18 | jangara mcholo road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | jangara mcholo road |  |  |  | -3.4638 | 38.3763 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/254/17-18 | Maintenance of Mwanjili mwakoto Road-Rmlf | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Maintenance of Mwanjili mwakoto Road-Rmlf |  |  |  | -3.5165 | 38.372 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/255/17-18 | Maintenance of DM Bridge RMLF | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Maintenance of DM Bridge RMLF | [6 empty] | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/256/17-18 | Construction of Mariwenyi social hall | Complete | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 3000000 | 100 | Construction of Mariwenyi socil hall |  |  |  | -3.437618 | 38.5095 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/257/17-18 | Construction of Shelemba socil hall | Complete | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 2000000 | 100 | Construction of Shelemba socil hall |  |  |  | -3.433981 | 38.4705 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/258/17-18 | Complition of Mariwenyi social hall | Complete | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 3500000 | 100 | Complition of Mariwenyi social hall |  |  |  | -3.437618 | 38.5095 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/259/17-18 | Wughanangu Road Culverting | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 500000 | 100 | Cultvering Wughanangu road | [6 empty] | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/260/17-18 | Ngerenyi Mwalekwa Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Ngerenyi Mwalekwa Road |  |  |  | -3.418577 | 38.3309 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/261/17-18 | Ngiriwunyi Footpath | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 300000 | 100 | Ngiriwunyi Footpath |  |  |  | -3.436376 | 38.3763 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/262/17-18 | Maintenance of Chongonyi Kizingo | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Maintenance of Chongonyi Kizingo |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/263/17-18 | Kilulunyi Vichwala road (Spot murraming and Culverting) | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Spot murraming and Culverting Kilulunyi Vichwala road |  |  |  | -3.463261 | 38.3421 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/264/17-18 | Murray Josa road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 126931 | 100 | Murray Josa road |  |  |  | .-3.449312 | 38.3637 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/265/17-18 | Rehabilitation Of chae solome road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 800000 | 100 | Rehabilitation Of chae solome road |  |  |  | -3.463261 | 38.3421 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/266/17-18 | Rehabilitation Of kichechunyi macha | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 800000 | 100 | Rehabilitation Of kichechunyi macha |  |  |  | -3.422784 | 38.3434 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/267/17-18 | Maintenance of Mlangonyi Kishamba | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Maintenance of Mlangonyi Kishamba |  |  |  | -3.455343 | 38.3704 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/268/17-18 | Culverting of kisaghala ngerenyi | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Culverting of kisaghala ngerenyi |  |  |  | -3.435250 | 38.3414 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/269/17-18 | Maintenance of bura mararo | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Maintenance of bura mararo |  |  |  | -3.458585 | 38.3397 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/270/17-18 | Culverting of Kinani Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 600000 | 100 | Culverting of Kinani Road |  |  |  | -3.436376 | 38.3763 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/271/17-18 | Mwangoji Kisaghala Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1900000 | 100 | Mwangoji Kisaghala Road |  |  |  | -3.435250 | 38.3414 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/272/17-18 | Levelling of Vichwala and Kidaya Playing fields | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Levelling of Vichwala and Kidaya Playing fields |  |  |  | -3.422954 | 38.3188 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/273/16-17 | Variation Mwatate water Supply | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Variation Mwatate water Supply | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/274/16-17 | MWASINENYI WATER PROJECT | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | MWASINENYI WATER PROJECT | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/275/16-17 | Purchase of 4 water tanks - (peleleza 2, Soko ya zamani 2,@ 10,000 litres) | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Purchase of 4 water tanks - (peleleza 2, Soko ya zamani 2,@ 10,000 litres) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/276/16-17 | Mwasinenyi borehole - mwatate ward (pending bills) | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Mwasinenyi borehole - mwatate ward (pending bills) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/277/16-17 | Kipusi Ecd construction - pending bill | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Kipusi Ecd construction - pending bill | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/278/16-17 | Josa - Modambogho Water supply | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Josa - Modambogho Water supply | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/279/16-17 | Kipusi bore hole-Extension supply to Mwatate town | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Kipusi bore hole-Extension supply to Mwatate town | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/280/16-17 | CONSTRUCTION MSISINENYI ECD | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | CONSTRUCTION MSISINENYI ECD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/281/16-17 | CONSTRUCTION MWATUNGE ECD | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | CONSTRUCTION MWATUNGE ECD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/282/16-17 | CONSTRUCTION MWANDALA ECD | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | CONSTRUCTION MWANDALA ECD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/283/16-17 | Furnishing and equipping allECDEs in Mwatate | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Furnishing and equipping allECDEs in Mwatate | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/284/16-17 | Construction of Mlamenyi YP twin workshop block | Complete | 2016-2017 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Construction of Mlamenyi YP twin workshop block | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/285/16-17 | Construction of Mwatate ECDE | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of Mwatate ECDE | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/286/16-17 | MLAMBENYI YOUTH POLYTECHNIC FURNITURE | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | MLAMBENYI YOUTH POLYTECHNIC FURNITURE | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/287/16-17 | CONSTRUCTION OF A LIBRARY - MWATUNGE | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | CONSTRUCTION OF A LIBRARY - MWATUNGE | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/288/16-17 | MODAMBOGHO DISPENSARY (Fencing) | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | MODAMBOGHO DISPENSARY (Fencing) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/289/16-17 | Youth, Sports, Gender and Social Services | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Youth, Sports, Gender and Social Services | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/290/16-17 | Mwatunge kizina footpath | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Mwatunge kizina footpath | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/291/16-17 | Msisineni,Makombenyi road | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Msisineni,Makombenyi road | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/292/16-17 | IMPROVEMENT & MURRAMING OF ZIWA LA NGOMBE ROAD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | IMPROVEMENT & MURRAMING OF ZIWA LA NGOMBE ROAD | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/293/16-17 | Msisineni,Makombenyi road | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Msisineni,Makombenyi road | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/294/16-17 | Installation of Culvers singila gandia | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Installation of Culvers singila gandia | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/295/16-17 | Mengo road | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Mengo road | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/296/16-17 | Mwatate boda boda shed the office | Complete | 2016-2017 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Mwatate boda boda shed the office | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/297/16-17 | Mwatate boda boda shed junction | Complete | 2016-2017 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Mwatate boda boda shed junction | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/298/16-17 | Mwatate boda boda shed baisanda | Complete | 2016-2017 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Mwatate boda boda shed baisanda | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/299/16-17 | Mtito women empowerment group | Complete | 2016-2017 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Mtito women empowerment group | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/300/16-17 | Completion of Mbagha Staff House | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | COMPLETION OF MBAGHA STAFF HOUSE |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/301/16-17 | CONSTRUCTION OF MWASHOTI ECDE | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 880367 | 100 | CONSTRUCTION OF MWASHOTI ECDE |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/302/16-17 | Construction of Kighombo YP twin workshop | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 3636793 | 100 | Construction of Kighombo YP twin workshop |  |  |  | -3.393253 | 38.4457 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/303/16-17 | Construction of Mselia YP twin workshop | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1100000 | 100 | Construction of Mselia YP twin workshop |  |  |  | -3.437168 | 38.5095 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/304/16-17 | Marumbenyi ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 400000 | 100 | Marumbenyi ECD |  |  |  | -3.4293943 | 38.4385 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/305/16-17 | Mwakinyungu ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 200000 | 100 | Mwakinyungu ECD |  |  |  | -3.4265578 | 38.4234 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/306/16-17 | Ronge primary ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 200000 | 100 | Ronge primary ECD |  |  |  | -3.336523 | 38.3875 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/307/16-17 | Ndile ronge juu ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 500000 | 100 | Ndile ronge juu ECD | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/308/16-17 | Construction of Mwakaleri ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1193564 | 100 | Construction of Mwakaleri ECD |  |  |  | -3.356297 | 38.401 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/309/16-17 | Construction of Rahai ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1193564 | 100 | Construction of Rahai ECD |  |  |  | -3.379925 | 38.4345 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/310/16-17 | Construction of Baghau ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1499062.2 | 100 | Construction of Baghau ECD | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/311/16-17 | Construction of Nganjinyi ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1233295 | 100 | Construction of Nganjinyi ECD |  |  |  | -3.434643 | 38.4395 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/312/16-17 | Construction of Shelemba merternity block | Complete | 2016-2017 | n/a | 0 | Health Services | County Government | [7 empty] | 1000000 | 100 | Construction of Shelemba merternity block |  |  |  | -3.433918 | 38.4705 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/313/16-17 | Shelemba mvita and kighononyi sreet light | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 200000 | 100 | Shelemba mvita and kighononyi sreet light | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/314/16-17 | Construction of Mwangea ECD | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1500000 | 100 | Construction of Mwangea ECD | [6 empty] | County Government | 100 |  |  | RONGE | Admin 3
006/133/315/16-17 | Construction of Marumbenyi ECDE | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 700000 | 100 | Construction of Marumbenyi ECDE |  |  |  | -3.4293943 | 38.4385 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/316/16-17 | Kilambi Road | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 100000 | 100 | Kilambi Road |  |  |  | -3,463461 | 38.3388 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/317/16-17 | Kilulunyi Vichwala road | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 100000 | 100 | Kilulunyi Vichwala road |  |  |  | -3.488494 | 38.322 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/318/16-17 | Josa Chongonyi Road | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 100000 | 100 | Josa Chongonyi Road |  |  |  | -3.430071 | 38.3602 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/319/16-17 | Bura-Mararo road | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 100000 | 100 | Bura-Mararo road |  |  |  | -3.458585 | 38.3397 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/320/16-17 | Murray Josa road | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1200000 | 100 | Murray Josa road |  |  |  | -3.449312 | 38.3633 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/321/16-17 | Mwangoji Kisaghala road | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1200000 | 100 | Mwangoji Kisaghala road |  |  |  | -3.435250 | 38.3414 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/322/15-16 | Crush construction at Mwatate Ward (pending Bill) | Complete | 2015-2016 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 0 | 100 | Crush construction at Mwatate Ward (pending Bill) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/323/15-16 | Mwasinenyi water project | Complete | 2015-2016 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Mwasinenyi water project | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/324/15-16 | Mwasinenyi borehole - mwatate ward (pending bills) | Complete | 2015-2016 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Mwasinenyi borehole - mwatate ward (pending bills) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/325/15-16 | Josa - Modambogho Water supply | Complete | 2015-2016 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Josa - Modambogho Water supply | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/326/15-16 | Kipusi bore hole-Extension supply to Mwatate town | Complete | 2015-2016 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Kipusi bore hole-Extension supply to Mwatate town | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/327/15-16 | Mwatate Ecde Classroom | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Mwatate Ecde Classroom | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/328/15-16 | Kipusi Ecde Classroom | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Kipusi Ecde Classroom | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/329/15-16 | Mlambenyi youth polytechnic twin classes | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Mlambenyi youth polytechnic twin classes | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/330/15-16 | Modambogho dispensary laboratory | Complete | 2015-2016 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Modambogho dispensary laboratory | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/331/15-16 | Sports league | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Sports league | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/332/15-16 | Driving course | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Driving course | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/333/15-16 | Security streetlights : Landi maili kumi | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Security streetlights : Landi maili kumi | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/334/15-16 | Security streetlights : Junction - singila | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Security streetlights : Junction - singila | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/335/15-16 | Security streetlights : Junction - Kenyatta high school | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Security streetlights : Junction - Kenyatta high school | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/336/15-16 | Security streetlights : Baisanda - singila | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Security streetlights : Baisanda - singila | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/337/15-16 | Mwatunge kizina Footpath | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1400000 | 100 | Mwatunge kizina Footpath |  |  |  | -3.4969 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/338/15-16 | msisinenyi makombenyi | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | msisinenyi makombenyi |  |  |  | -3.4564 | 38.3763 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/339/15-16 | constraction of mwatate sub county head quarters office | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | constraction of mwatate sub county head quarters office | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/340/15-16 | Mwatate Secondary hostle | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Mwatate Secondary hostle | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/341/15-16 | Mwatunge kizina footbridges 3no | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 698664 | 100 | Mwatunge kizina footbridges 3no |  |  |  | -3.4969 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/342/15-16 | fighinyi mwatunge kizina | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 940662 | 100 | fighinyi mwatunge kizina |  |  |  | -3.4969 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/343/15-16 | Bodaboda shades - mwatate The office | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Bodaboda shades - mwatate The office | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/344/15-16 | Bodaboda shades - mwatate Maryland | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Bodaboda shades - mwatate Maryland | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/345/15-16 | Bodaboda shades - mwatate Landimaili kumi | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Bodaboda shades - mwatate Landimaili kumi | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/346/15-16 | Bodaboda shades - mwatate Junction | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Bodaboda shades - mwatate Junction | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/347/15-16 | Bodaboda shades - mwatate Baisanda | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Bodaboda shades - mwatate Baisanda | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/348/15-16 | Public toilet Landi maili kumi | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Public toilet Landi maili kumi | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/349/15-16 | Mwatate 1 no boda boda shed | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Mwatate 1 no boda boda shed | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/350/15-16 | Construction of Mwakitau Health Centre | Complete | 2015-2016 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | CONSTRUCTION OF MWAKITAU HEALTH CENTER |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/351/15-16 | Erection of Streetlights at Bura Market | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 6000000 | 100 | ERECTION OF STREETLIGHTS AT BURA MARKET |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/352/15-16 | Construction of Barawa ECDE | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1156957 | 100 | CONSTRUCTION OF BARAWA ECDE |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/353/15-16 | Kirongwe Road Rehabillitation | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Kirongwe Road Rehabillitation |  |  |  | -3.5164 | 38.372 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/354/15-16 | bridge (lerirongwe) - lerinyi footbridge | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | bridge (lerirongwe) - lerinyi footbridge |  |  |  | -3.5115 | 38.3691 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/355/15-16 | mwatate mwanganga mruru culvert | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | mwatate mwanganga mruru culvert |  |  |  | -3.4699 | 38.3451 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/356/15-16 | mkuyuni wumari mwamkolo road culvert | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | mkuyuni wumari mwamkolo road culvert |  |  |  | -3.5107 | 38.2551 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/357/15-16 | manganga irarenyi road | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | manganga irarenyi road |  |  |  | -3.5018 | 38.3704 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/358/15-16 | mwatate manganga mruru rd | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 |  |  |  |  | -3.4699 | 38.3451 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/359/15-16 | mwatate manganga mruru rd | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | mwatate manganga mruru rd |  |  |  | -3.4699 | 38.3451 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/360/15-16 | Public Toilet At Kamtonga Trading Centre | Complete | 2015-2016 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Public Toilet At Kamtonga Trading Centre |  |  |  | -3.3969 | 38.5571 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/361/15-16 | Construction Of ChungaUnga ECDE | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction Of ChungaUnga ECDE |  |  |  | -3.6038 | 38.3115 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/362/15-16 | Construction of Alia ECD (CHAWIA WARD WDF) | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of Alia ECD (CHAWIA WARD WDF) |  |  |  | -3.4806 | 38.2696 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/363/15-16 | Construction of Manowa ECD (Chawia Ward WDF) | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of Manowa ECD (Chawia Ward WDF) |  |  |  | -3.5877 | 38.3329 |  | County Government | 100 |  |  | CHAWIA | Admin 3
006/133/364/15-16 | Shelemba ECDE | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1118409 | 100 | Shelemba ECDE |  |  |  | -3.434314 | 38.4698 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/365/15-16 | Construction of Ndembonyi ECD | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1698489 | 100 | Construction of Ndembonyi ECD |  |  |  | -3.450648 | 38.3523 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/366/15-16 | Construction of Mariwenyi ECD | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1188409 | 100 | Construction of Mariwenyi ECD |  |  |  | -3.441730 | 38.5073 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/367/15-16 | Construction of Kironge ECD | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 878888 | 100 | Construction of Kironge ECD |  |  |  | -3.371339 | 38.4296 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/368/15-16 | Construction of ECD Mengo | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 950554 | 100 | Construction of ECD Mengo |  |  |  | -3.436802 | 38.4737 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/369/15-16 | Construction of ECD Mambura | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 987220 | 100 | Construction of ECD Mambura |  |  |  | -3.426578 | 38.4234 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/370/15-16 | Construction of Mrabenyi ECD | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 750000 | 100 | Construction of Mrabenyi ECD |  |  |  | -3.40814 | 38.4855 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/371/15-16 | Saghaighu Playing field | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 500000 | 100 |  |  |  |  | -3.422954 | 38.3188 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/372/15-16 | Rehabilitation Of Playing Field Vichwala | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 500000 | 100 | Rehabilitation Of Playing Field Vichwala |  |  |  | -3.488494 | 38.322 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/373/15-16 | Rehabilitation of Playing Fields Mrashinyi t/c - To be issued to Kidaya/Saghaighu | Complete | 2015-2016 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 500000 | 100 | Rehabilitation of Playing Fields Mrashinyi t/c - To be issued to Kidaya/Saghaighu |  |  |  | -3.422954 | 38.3188 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/374/14-15 | Constrction of crush pens -Mwatate (Rebudgeted) | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Constrction of crush pens -Mwatate (Rebudgeted) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/375/14-15 | Mwatate-Mwasinenyi Water Supply(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Mwatate-Mwasinenyi Water Supply(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/376/14-15 | Kipusi bore hole-Extension supply to Mwatate town(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Water, Sanitation, Environment, Climate Change and Natural Resources | County Government | [7 empty] | 0 | 100 | Kipusi bore hole-Extension supply to Mwatate town(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/377/14-15 | Construction ofECD-Mgeno(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction ofECD-Mgeno(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/378/14-15 | Construction of ECD-Mwatate(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of ECD-Mwatate(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/379/14-15 | Construction ofECD-Kipusi(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction ofECD-Kipusi(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/380/14-15 | ECD-Mazola(Furnishing)(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | ECD-Mazola(Furnishing)(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/381/14-15 | Construction of ECD-Maili Kumi(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 0 | 100 | Construction of ECD-Maili Kumi(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/382/14-15 | Construction of maternity wing& lab( modambogho dispensary)(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Construction of maternity wing& lab( modambogho dispensary)(MWATATE WARD)-WDF | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/383/14-15 | completion of Maternity-Mwatate SDH) | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | completion of Maternity-Mwatate SDH) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/384/14-15 | Purchase of Physiotherapy equipment-SWD(Wesu,Mwatateand Taveta) | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Purchase of Physiotherapy equipment-SWD(Wesu,Mwatateand Taveta) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/385/14-15 | Purchase of Generators ( Wesu SCH, and Mwatate SCH) | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [7 empty] | 0 | 100 | Purchase of Generators ( Wesu SCH, and Mwatate SCH) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/386/14-15 | Fencing of Mwatate Youth Empowerment Centre 1 ha | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Fencing of Mwatate Youth Empowerment Centre 1 ha | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/387/14-15 | Purchase of computers and accessories for Mwatate YEC | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Purchase of computers and accessories for Mwatate YEC | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/388/14-15 | Purchase of Indoor games equipment for Mwatate YEC | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 0 | 100 | Purchase of Indoor games equipment for Mwatate YEC | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/389/14-15 | Preparation of 4 no. Urban Plans (Voi, Mwatate, Taveta, Mtito and Maungu) as per the Urban Areas and Cities Act and the County Government Act | Complete | 2014-2015 | n/a | 0 | Lands, Physical Planning, Mining and Urban Development | County Government | [7 empty] | 0 | 100 | Preparation of 4 no. Urban Plans (Voi, Mwatate, Taveta, Mtito and Maungu) as per the Urban Areas and Cities Act and the County Government Act | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/390/14-15 | Mwatate 1 no | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Mwatate 1 no | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/391/14-15 | Mwatate sub county infrastructural improvement (Rebudgeted) | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Mwatate sub county infrastructural improvement (Rebudgeted) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/392/14-15 | construction of eco lavatories and washrooms at Voi,Mwatate,Maungu,Wundanyi,Taveta& Mtito Andei) | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | construction of eco lavatories and washrooms at Voi,Mwatate,Maungu,Wundanyi,Taveta& Mtito Andei) | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/393/14-15 | Mwatunge-Kizina (MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 700000 | 100 | Mwatunge-Kizina (MWATATE WARD)-WDF |  |  |  | -3.48 | 38.3383 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/394/14-15 | Mwatunge-Kizina foot path(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Mwatunge-Kizina foot path(MWATATE WARD)-WDF |  |  |  | -3.4969 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/395/14-15 | Singila-Madungunyi-Shaghala road(MWATATE WARD)-WDF | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | Singila-Madungunyi-Shaghala road(MWATATE WARD)-WDF |  |  |  | -3.4949 | 38.3952 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/396/14-15 | Construction of Mwatate bus park | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 800000 | 100 | Construction of Mwatate bus park | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3
006/133/397/14-15 | Feasibility and rehabilitation for Mwatate stadium | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 600000 | 100 | Feasibility and rehabilitation for Mwatate stadium |  |  |  | -3.4983 | 38.3992 |  | County Government | 100 |  |  | MWATATE | Admin 3
006/133/398/14-15 | Construction of Kongoni ECDE | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1400000 | 100 | CONSTRUCTION OF KONGONI ECDE |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/399/14-15 | Construction of Bura Public Toilet | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | CONSTRUCTION OF BURA PUBLIC TOILET |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/400/14-15 | Construction ofLangteni Social hall 2 toilets,1000 chairs and modification | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 4516007 | 100 | Construction ofLangteni Social hall 2 toilets,1000 chairs and modification |  |  |  | -3.426578 | 38.4234 |  | County Government | 100 |  |  | RONGE | Admin 3
006/133/401/14-15 | Rehabilitation of Playing Fields Mrashinyi t/c | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 500000 | 100 | Rehabilitation of Playing Fields Mrashinyi t/c |  |  |  | -3.449555 | 38.3642 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/402/14-15 | Rehabilitation of Playing Fields Josa t/c | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 500000 | 100 | Rehabilitation of Playing Fields Josa t/c |  |  |  | -3.455343 | 38.3704 |  | County Government | 100 |  |  | Wusi/Kishamba | Admin 3
006/133/403/13-14 | Construction of Bura Public Toilet | Complete | 2013-2014 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 200000 | 100 | Construction of Bura Public Toilet |  |  |  | -3.5006 | 38.3174 |  | County Government | 100 |  |  | Bura | Admin 3
006/133/404/13-14 | Fire water point -Mwatate | Complete | 2013-2014 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 0 | 100 | Fire water point -Mwatate | [6 empty] | County Government | 100 |  |  | MWATATE | Admin 3