## Compilled
Project Number | Project Title | Project Status | Financial Year | Contractor Name | Estimated Cost | Department | Implemented By | Partner | Expected Start Date | Expected End Date | Approval/Contract Number | Contract Period (Days) | Technical Rating | Completion Level | Amount Paid | Percentage of Funding (Source of Funds) | Total Percentage | Project Scope | Administrative Level | Project Location | Location Names | Latitude | Longitude | ID (Source of Funds) | Funded By (Source of Funds) | Partner (Source of Funds) | ID (Administrative Areas) | Admin (Administrative Areas) | Admin Level (Administrative Areas)
006/132/01/24-25 | Construction Of Sir Ramson Ecde Classroom | Complete | 2024-2025 | Victrax Engineering And Construction | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1795842.4 | 100 | 100 | Construction Of Sir Ramson Ecde Classroom |  |  | Chala | -3.2048 | 37.7352 |  | County Government |  |  | Chala | Admin 3
006/132/02/24-25 | Lessesia Ecde | Complete | 2024-2025 | Mubesiru Construction Ltd | 0 | Education, Libraries and VTCs | County Government |  |  |  | 296 |  |  |  | 1993460 | 100 | 100 | Construction Of 1 Class |  |  | Mahoo | 3.3684 | 37.6636 |  | County Government |  |  | Mahoo | Admin 3
006/132/03/24-25 | Nakuruto Ecde | Complete | 2024-2025 | Datush Enterprises Ltd | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 998090 | 100 | 100 | Construction Of Ecde |  |  | Mahoo | 3.3378 | 37.7143 |  | County Government |  |  | Mahoo | Admin 3
006/132/04/24-25 | Malkloriti B Ecde And 3 Door Toilet | Complete | 2024-2025 | Bonwal Constrction &Holding Ltd | 0 | Education, Libraries and VTCs | County Government |  |  |  | 308 |  |  |  | 997600 | 100 | 100 | Construction Of Ecde |  |  | Mahoo | 3.3695 | 37.692 |  | County Government |  |  | Mahoo | Admin 3
006/132/05/24-25 | Brighter Days -Lesesia Rroad | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Road Formation & Mmuurrraming |  |  | Mahoo | 3.7687 | 37.672 |  | County Government |  |  | Mahoo | Admin 3
006/132/06/24-25 | Completion Of Tangini Ecde Classroom | Complete | 2024-2025 | Aruba Contractors | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.4669 | 37.5434 |  | County Government |  |  | Mata | Admin 3
006/132/07/24-25 | Grading And Murraming Of Kangero Road | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Murraming Of Kangero Road |  |  | Mata | -3.3486 | 37.6541 |  | County Government |  |  | Mata | Admin 3
006/132/08/24-25 | Road Formation, Grading And Murraming Of Mamasafi Road | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Road Formation, Grading And Murraming |  |  | Mata | -3.3479 | 37.7 |  | County Government |  |  | Mata | Admin 3
006/132/09/24-25 | Grading And Murraming Of Utawala Road | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Slab At Mokoi Road And Culvert Installation At Utawala Road. |  |  | Mata | 3.4028 | 3772934 |  | County Government |  |  | Mata | Admin 3
006/132/10/24-25 | Maintanance Of Roads Of Mata Ward | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Maintanance Of Roads Of Mata Ward |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/11/24-25 | Road Formation, Grading And Murraming Of Grigan-Ngaa Road | Ongoing | 2024-2025 | Kenrich Company | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2000000 | 100 | 100 | Road Formation, Grading And Murraming Of Grigan-Ngaa Road |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/12/24-25 | Fuel For Road Maintanance In Mata Ward | Complete | 2024-2025 | Border Point | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2000000 | 100 | 100 | Fuel For Road Maintanance In Mata Ward |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/13/24-25 | Structures In Mokoi Road And Utawala Road | Ongoing | 2024-2025 | Bosker Ace Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999925.48 | 100 | 100 | Structures In Mokoi Road And Utawala Road |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/14/24-25 | Youth And Women Empowerment | Complete | 2024-2025 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Youth And Women Empowerment |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/15/24-25 | Murraming Of Kiwalwa-Mtisoni-Riata Ndogo Road | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Kiwalwa-Mtisoni-Riata Ndogo Road |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/16/24-25 | Murraming Of Gasheni-Riata Kubwa Road | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Gasheni-Riata Kubwa Road |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/17/24-25 | Murraming Of Ngutini-Maseketeni Road | Complete | 2024-2025 | Bonwal Construction And Holding Company Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2843450 | 100 | 100 | Murraming Of Ngutini-Maseketeni Road |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/18/24-25 | Murraming Of Ukambani-Majengo Road | Ongoing | 2024-2025 | Scheme Construction And Technology Designers Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1997608.16 | 100 | 100 | Murraming Of Ukambani-Majengo Road |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/19/24-25 | Murraming Of Ukambani-Mlimani-Madarasani Road | Ongoing | 2024-2025 | Ericia Investment Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 3399900 | 100 | 100 | Murraming Of Ukambani-Mlimani-Madarasani Road |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/20/24-25 | Murraming Of Marabani-Kambugu Road | Complete | 2024-2025 | Zavon Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1998630 | 100 | 100 | Murraming Of Marabani-Kambugu Road |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/21/24-25 | Fuel For Excavator For Roads And Canal Maintenance | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Fuel For Excavator For Roads And Canal Maintenance |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/22/24-25 | Purchase Of Tents And Chairs | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Purchase Of Tents And Chairs |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/23/24-25 | Community Empowerment | Complete | 2024-2025 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Community Empowerment |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/24/24-25 | Desilting Njoro Kubwa Canal | Complete | 2024-2025 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Clearing Of The Canal |  |  | Mboghoni | -3.4241 | 37.685 |  | County Government |  |  | Mboghoni | Admin 3
006/132/25/24-25 | Culvert Of Maseketeni Ngutini Road | Complete | 2024-2025 | Bonwal Construction And Holding Company Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2843450 | 100 | 100 | Upgraiding Of The Road |  |  | Mboghoni | -3.5024 | 37.7043 |  | County Government |  |  | Mboghoni | Admin 3
006/132/26/23-24 | Malkulority Ecde | Complete | 2023-2024 |  | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Class |  |  | Mahoo | 3.3494 | 37.7082 |  | County Government |  |  | Mahoo | Admin 3
006/132/27/23-24 | Youth Road California | Complete | 2023-2024 | Yakn International Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 992199 | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3792 | 37.673 |  | County Government |  |  | Mahoo | Admin 3
006/132/28/23-24 | Hyder Park Phase 1&2 | Complete | 2023-2024 | Ringoma Renovators | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1495193.6 | 100 | 100 | Construction Of Slab |  |  | Mahoo | 3.3738 | 37.6825 |  | County Government |  |  | Mahoo | Admin 3
006/132/29/23-24 | By Pass Nguru Road | Complete | 2023-2024 | Zavon Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1658300 | 100 | 100 | Murrummung Road |  |  | Mahoo | 3.3687 | 37.666 |  | County Government |  |  | Mahoo | Admin 3
006/132/30/23-24 | Lessesia Primary Road | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3792 | 37.673 |  | County Government |  |  | Mahoo | Admin 3
006/132/31/23-24 | Ebennezer Kilimanjaro Rd Konoike | Complete | 2023-2024 | Yakyn International Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 999980 | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3373 | 37.6737 |  | County Government |  |  | Mahoo | Admin 3
006/132/32/23-24 | Danida Hall | Complete | 2023-2024 | Mushedede Royale Ltd P.O Box 263-90200 Kitui | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 499032 | 100 | 100 | Renovation Of The Hall |  |  | Mahoo | 3.3897 | 37.703 |  | County Government |  |  | Mahoo | Admin 3
006/132/33/23-24 | Construction Of Ndilidau Ecd Classroom | Complete | 2023-2024 | Maze Logistics And Supplies Limited | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1399999.36 | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.3499 | 37.6174 |  | County Government |  |  | Mata | Admin 3
006/132/34/23-24 | Construction Of Mata Ecd Classroom | Complete | 2023-2024 | Triplux Limited | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1384650 | 100 | 100 | Construction Of 1 Classroom |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/35/23-24 | Construction Of Kimondia Ecd Classroom | Complete | 2023-2024 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Kimondia Ecd Classroom |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/36/23-24 | Construction Of Tangaini Ecd Classroom | Complete | 2023-2024 | Aruba Construction Limited | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1391918 | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.4157 | 37.6757 |  | County Government |  |  | Mata | Admin 3
006/132/37/23-24 | Fencing Of Phase Ii Kimala Ecd | Complete | 2023-2024 | Vulmatt Kenya Limited | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 2099990 | 100 | 100 | Fencing Construction |  |  | Mata | -3.3622 | 37.6322 |  | County Government |  |  | Mata | Admin 3
006/132/38/23-24 | Rehabilitation And Grading Of Mata Ward Roads | Complete | 2023-2024 | Blue Avenue Ventures | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2400000 | 100 | 100 | Rehabilitation And Grading Of Mata Ward Roads |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/39/23-24 | Youth And Women Empowerment | Complete | 2023-2024 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Youth And Women Empowerment |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/40/23-24 | Supply Of Beds And Mattresses For Kitobo Dispensary- | Ongoing | 2023-2024 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni | -3.4413 | 37.6053 |  | County Government |  |  | Mboghoni | Admin 3
006/132/41/23-24 | Formation And Murraming Of Njoro-Lotima A Road | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni | -3.4401 | 37.6123 |  | County Government |  |  | Mboghoni | Admin 3
006/132/42/23-24 | Grading And Murraming Of Kitoghoto-Ngutini Road | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/43/23-24 | Slabbing Of A Drift At Njoro-Lotima B Road | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/44/23-24 | Formation And Murraming Of Ukambani-Mlimani Road | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/45/23-24 | Grading And Murraming Of Maseketeni-Lambo-Abori Road | Complete | 2023-2024 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/46/23-24 | Purchase Of Motor Cycles For Youths Empowerment | Complete | 2023-2024 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/47/22-23 | Light Grading And Murraming Of Califonia Road (Airstrip-Mosque | Complete | 2022-2023 | Blue Avenue Ventures | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | 100 | Light Grading And Murraming Of Califonia Road (Airstrip-Mosque |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/48/22-23 | Light Grading Oftimbila By Pass-Round About -Darajani | Complete | 2022-2023 | Blue Avenue Ventures | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | 100 | Light Grading Oftimbila By Pass-Round About -Darajani |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/49/22-23 | Grading Of Kitondoni -Timbila Road | Complete | 2022-2023 | Saleh Construction And Roadworks Ltd | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2000000 | 100 | 100 | Grading Of Kitondoni -Timbila Road |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/50/22-23 | Installation Of Kasokoni-Kisuu Box Culvert | Complete | 2022-2023 | Idha Enterprises Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1500000 | 100 | 100 | Installation Of Kasokoni-Kisuu Box Culvert |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/51/22-23 | Slabbing Of Hyder Park Road | Complete | 2022-2023 | Muhadhi Brothers Trading Co. | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government |  |  |  | 1167667 |  |  |  | 1267203.12 | 100 | 100 | Slabbing Of Hyder Park Road |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/52/22-23 | Kimala Ecde Fencing | Complete | 2022-2023 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Fencing Construction |  |  | Mata | -3.6551 | 37.4126 |  | County Government |  |  | Mata | Admin 3
006/132/53/22-23 | Development Of Rekeke Vtcs | Complete | 2022-2023 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Purchasing Of Equipment |  |  | Mata | -3.8564 | 36.2357 |  | County Government |  |  | Mata | Admin 3
006/132/54/22-23 | Development Of Wards Vtcs | Complete | 2022-2023 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Development Of Wards Vtcs |  |  | Mata |  |  |  | County Government |  |  |  | Admin 3
006/132/55/22-23 | Renovation Of Jipe Dispensary | Complete | 2022-2023 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Renovation Of Kachero Dispensary Construction Of 1 Classroom |  |  | Mata | -3.5548 | 37.7471 |  | County Government |  |  | Mata | Admin 3
006/132/56/22-23 | Purchase Of Fertilizers To Rice Farmers Of Uswi Cooperative | Complete | 2022-2023 | Banane North Explorers Limited | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 1800000 | 100 | 100 | Purchase Of Fertilizers To Rice Farmers Of Uswi Cooperative |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/57/22-23 | Finishing Of Milk Cooling Plant In Eldoro | Complete | 2022-2023 | Aruba Construction And General Merchants | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [7 empty] | 597852.4 | 100 | 100 | Finishing Of Milk Cooling Plant In Eldoro |  |  | Mboghoni | -3.4825 | 37.6738 |  | County Government |  |  | Mboghoni | Admin 3
006/132/58/22-23 | Renovation Of Kimorigo Storage Warehouse | Complete | 2022-2023 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Renovation Of Kimorigo Storage Warehouse |  |  | Mboghoni |  |  |  | County Government |  |  |  | Admin 3
006/132/59/22-23 | Construction Ofmaseketeni Ecde | Complete | 2022-2023 | Colha Investments | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1,579,514.00 | 100 | 100 | Construction Ofmaseketeni Ecde |  |  | Mboghoni | -3.4946 | 37.7131 |  | County Government |  |  | Mboghoni | Admin 3
006/132/60/22-23 | Equipping Of Kambugu Vtc | Complete | 2022-2023 | Peacecom Data Solution Limited | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 500000 | 100 | 100 | Equipping Of Kambugu Vtc |  |  | Mboghoni | -3.436 | 37.6158 |  | County Government |  |  | Mboghoni | Admin 3
006/132/61/22-23 | Development Of Wards Vtcs | Complete | 2022-2023 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Development Of Wards Vtcs |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/62/22-23 | Murraming Of Majengo Buruma Road | Complete | 2022-2023 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Majengo Buruma Road |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/63/22-23 | Fueling Of Mboghoni Excavator And Servicing | Complete | 2022-2023 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Fueling Of Mboghoni Excavator And Servicing |  |  | Mboghoni | -3.3968 | 37.6848 |  | County Government |  |  | Mboghoni | Admin 3
006/132/64/22-23 | Eldoro-Kisimani Solar Panels And Fittings | Complete | 2022-2023 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Eldoro-Kisimani Solar Panels And Fittings |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/65/22-23 | Supply & Delivery Of Sport Items, Plastic Chairs & Water Tanks | Complete | 2022-2023 | Faxtech Company Limited | 0 | Youth, Sports, Gender and Social Services | County Government | [7 empty] | 1697500 | 100 | 100 | Supply & Delivery Of Sport Items, Plastic Chairs & Water Tanks |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/66/22-23 | Rehabilitation Of Njoro Lotima Road | Complete | 2022-2023 | Sangenyi General Limited | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 4100000 | 100 | 100 | Rehabilitation Of Njoro Lotima Road |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/67/22-23 | Rice Mill Plant | Ongoing | 2022-2023 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Rice Mill Plant |  |  | Mboghoni | -3.3968 | 37.6748 |  | County Government |  |  | Mboghoni | Admin 3
006/132/68/21-22 | Mahoo Ward Wide Roads | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Maintenance And Rehabilitation |  |  | Mahoo | 3.5182 | 38.6103 |  | County Government |  |  | Mahoo | Admin 3
006/132/69/21-22 | Purchase Of Milling Machine For Single Cell Anaemia Group (Kisiagi) | Complete | 2021-2022 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Purchase Of Milling Machine For Single Cell Anaemia Group (Kisiagi) |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/70/21-22 | Pump And Accessories For Kassaani Borehole | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Pump And Accessories For Kassaani Borehole |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/71/21-22 | Dry Hiring Of Excavator For Desilting Canal In Mata Ward | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Dry Hiring Of Excavator For Desilting Canal In Mata Ward |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/72/21-22 | Fuel For Desilting Canals In Mata Ward | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Fuel For Desilting Canals In Mata Ward |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/73/21-22 | Completion Of Two Classrooms (Grogan Ecde) | Complete | 2021-2022 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Completion Of Two Classrooms (Grogan Ecde) |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/74/21-22 | Formation Of Kimondia - Chachewa - Ngaa Road(Ongoing) | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | New Road Formation |  |  | Mata | -3.3465 | 37.7076 |  | County Government |  |  | Mata | Admin 3
006/132/75/21-22 | Formation Of Grigan - Ngaa Road | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | New Road Formation |  |  | Mata | -3.3547 | 37.4668 |  | County Government |  |  | Mata | Admin 3
006/132/76/21-22 | Opening And Grading Of Mtakuja Sand Harvesting Road | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Bush Clearing And Grading |  |  | Mata | -3.4348 | 37.6779 |  | County Government |  |  | Mata | Admin 3
006/132/77/21-22 | Grading And Murraming Of Ndilidau Roads | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Murraming |  |  | Mata | -3.5769 | 37.4674 |  | County Government |  |  | Mata | Admin 3
006/132/78/21-22 | Grading And Murraming Of Mwakoi Road | Complete | 2021-2022 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Murraming |  |  | Mata | -3.3774 | 37.7105 |  | County Government |  |  | Mata | Admin 3
006/132/79/20-21 | Chumvini Bodaboda Shed | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Bodaboda Shed |  |  | Chala | -3.2094 | 37.7116 |  | County Government |  |  | Chala | Admin 3
006/132/80/20-21 | Chokaa Ecde | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Class |  |  | Chala | -3.2068 | 37.7179 |  | County Government |  |  | Chala | Admin 3
006/132/81/20-21 | Phase One Kidongu Dispensary | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 4000000 | 100 | 100 | Construction Of Dispensary |  |  | Chala | -3.3521 | 37.7376 |  | County Government |  |  | Chala | Admin 3
006/132/82/20-21 | Mahandakini Fence | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Fence |  |  | Chala | -3.2468 | 37.7279 |  | County Government |  |  | Chala | Admin 3
006/132/83/20-21 | Uthiani Footbridge | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Footbridge |  |  | Chala | -3.1828 | 37.704 |  | County Government |  |  | Chala | Admin 3
006/132/84/20-21 | Muusini Toilet & Tank | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Toilet |  |  | Chala | -3.2036 | 37.7013 |  | County Government |  |  | Chala | Admin 3
006/132/85/20-21 | Kalambani Fence | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Fencing Ecde Compound |  |  | Chala | -3.2866 | 37.7281 |  | County Government |  |  | Chala | Admin 3
006/132/86/20-21 | Phase 2 Fencing Of Chala Dispensary | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 994945 | 100 | 100 | Construction Of Disp Fence |  |  | Chala | -3.2955 | 37.7357 |  | County Government |  |  | Chala | Admin 3
006/132/87/20-21 | Chala Disp. Fence | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Disp Fence |  |  | Chala | -3.2955 | 37.7357 |  | County Government |  |  | Chala | Admin 3
006/132/88/20-21 | Irrigation Ecde | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Class |  |  | Chala | -3.2133 | 37.7518 |  | County Government |  |  | Chala | Admin 3
006/132/89/20-21 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/90/20-21 | Kirimeri Nursery Perimeter Fence | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ecde |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/91/20-21 | Maklortiti Dispensary Equipment | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 745000 | 100 | 100 | Equpping Of Dispensary |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/92/20-21 | Malkulority Ecde | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Class |  |  | Mahoo | 3.3494 | 37.7082 |  | County Government |  |  | Mahoo | Admin 3
006/132/93/20-21 | Nakuruto Ecde | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Ecde |  |  | Mahoo | 3.3378 | 37.7143 |  | County Government |  |  | Mahoo | Admin 3
006/132/94/20-21 | Kremeri Ecde Kitchen | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Kitchen |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/95/20-21 | Mahoo Ecde Kitchen | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Kitchen |  |  | Mahoo | 3.473 | 38.5849 |  | County Government |  |  | Mahoo | Admin 3
006/132/96/20-21 | Msengoni Road Opening | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 3400000 | 100 | 100 | Road Formation |  |  | Mahoo | 3.3939 | 37.7121 |  | County Government |  |  | Mahoo | Admin 3
006/132/97/20-21 | Majengo Mahoo Rd | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrrumming And Copaction |  |  | Mahoo | 3.3955 | 37.6795 |  | County Government |  |  | Mahoo | Admin 3
006/132/98/20-21 | St. Gregor Raashia A | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Slabbing Of Thr Road |  |  | Mahoo | 3.3913 | 37.6797 |  | County Government |  |  | Mahoo | Admin 3
006/132/99/20-21 | Boda Boda Shed Devine Flavour Cllr. Mathew Rd | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming And Compaction |  |  | Mahoo | 3.3829 | 37.6797 |  | County Government |  |  | Mahoo | Admin 3
006/132/100/20-21 | Mata Youth Polytechnic | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Mata Vtc |  |  | Mata | -3.3906 | 37.5853 |  | County Government |  |  | Mata | Admin 3
006/132/101/20-21 | Completion Of Kachero Dispensary | Complete | 2020-2021 | n/a | 0 | Health Services | County Government | [7 empty] | 1850000 | 100 | 100 | Construction Of Kachero Dispensary |  |  | Mata | -3.4802 | 37.3478 |  | County Government |  |  | Mata | Admin 3
006/132/102/20-21 | Construction Of A Toilet At Kachero Dispensary | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Toilet At Kachero Dispensary |  |  | Mata | -3.4772 | 37.6146 |  | County Government |  |  | Mata | Admin 3
006/132/103/20-21 | Construction Of A Toilet At Mata Dispensary | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1000000 | 100 | 100 | Construction Of The Toilet At Mata Dispensary |  |  | Mata | -3.8968 | 37.5557 |  | County Government |  |  | Mata | Admin 3
006/132/104/20-21 | Kimondia - Ngaa Road | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Murraming |  |  | Mata | -3.4289 | 37.7001 |  | County Government |  |  | Mata | Admin 3
006/132/105/20-21 | Mwakoi Road Bush Clearing/Grading1300000 | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Mokoi Road Bush Clearing |  |  | Mata | -3.4029 | 37.7268 |  | County Government |  |  | Mata | Admin 3
006/132/106/20-21 | Timbila - Mkuyuni - Rekeke Road Bush Clearing And Grading | Complete | 2020-2021 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Bush Clearing |  |  | Mata | -3.4316 | 37.7179 |  | County Government |  |  | Mata | Admin 3
006/132/107/20-21 | Dairy Cows For Wazee | Complete | 2020-2021 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Dairy Cows For Wazee |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/108/20-21 | Mata Youth Polytechnic | Complete | 2020-2021 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Mata Youth Polytechnic |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/109/20-21 | Eldoro Milk Cooling Plant | Complete | 2020-2021 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Eldoro Milk Cooling Plant |  |  | Mboghoni | -3.4825 | 37.6738 |  | County Government |  |  | Mboghoni | Admin 3
006/132/110/20-21 | Purchase Of Rice Value Addition Machine | Ongoing | 2020-2021 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Purchase Of Rice Value Addition Machine |  |  | Mboghoni | -3.3968 | 37.6748 |  | County Government |  |  | Mboghoni | Admin 3
006/132/111/19-20 | Sir Ramson Rd | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading & Gravelling Of Ramson Rd |  |  | Chala | -3.1906 | 37.7269 |  | County Government |  |  | Chala | Admin 3
006/132/112/19-20 | Chala Chini Rd | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.3342 | 37.7354 |  | County Government |  |  | Chala | Admin 3
006/132/113/19-20 | Timboni Kwa Edward Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murumming Of The Road |  |  | Mahoo | 3.349 | 37.703 |  | County Government |  |  | Mahoo | Admin 3
006/132/114/19-20 | Murraming Of Mbochi-Kijuijui Road | Complete | 2019-2020 | Niko Genral Agencies | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1995640 | 100 | 100 | Murumming Of The Road |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/115/19-20 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1039995 | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/116/19-20 | Kirimeri Nursery Perimeter Fence | Complete | 2019-2020 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ecde |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/117/19-20 | Langata Bypass Barrier Constructionroad | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 588120 | 100 | 100 | Murrummung Road |  |  | Mahoo | 3.3742 | 37.6823 |  | County Government |  |  | Mahoo | Admin 3
006/132/118/19-20 | Completion Of Msengonyi Road, Murraming | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1902338 | 100 | 100 | Murrumming Of The Road |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/119/19-20 | Murraming Of Gorofani-Makau Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 948636 | 100 | 100 | Murruming Of The Road |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/120/19-20 | Mahoo Ecde Kitchen | Complete | 2019-2020 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Kitchen |  |  | Mahoo | 3.473 | 38.5849 |  | County Government |  |  | Mahoo | Admin 3
006/132/121/19-20 | Kirimeri Nursery Perimeter Fence | Complete | 2019-2020 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ecde |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/122/19-20 | Routine Maintenace And Spot Improvement | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Routine Maintenace And Spot Improvement |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/123/19-20 | Installation Of One Box Culvert And Double 900 Mm Culvert At Mkuyuni Kingwareni Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Box Culvert Installation |  |  | Mata | -3.6479 | 37.7987 |  | County Government |  |  | Mata | Admin 3
006/132/124/19-20 | Routine Maintenace And Spot Improvement | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Routine Maintenace And Spot Improvement |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/125/19-20 | Murraming Of Kwa Father Moya Moya Mtisoni Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Kwa Father Moya Moya Mtisoni Road |  |  | Mboghoni | -3.4338 | 37.6849 |  | County Government |  |  | Mboghoni | Admin 3
006/132/126/19-20 | Murraming Of Eldoro Kitoghoto Ngutini Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Eldoro Kitoghoto Ngutini Road |  |  | Mboghoni | -3.4763 | 3.4946 |  | County Government |  |  | Mboghoni | Admin 3
006/132/127/19-20 | Excavation Of Msengone Python Hill |  | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Excavation Of Msengone Python Hill |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/128/19-20 | Excavation Of Lambo Maseketeni Road | Complete | 2019-2020 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Excavation Of Lambo Maseketeni Road |  |  | Mboghoni | -3.4946 | 37.7131 |  | County Government |  |  | Mboghoni | Admin 3
006/132/129/18-19 | Chala Madukani 4 Door Toilet | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Madukani Door Toilet |  |  | Chala | -3.2946 | 37.7339 |  | County Government |  |  | Chala | Admin 3
006/132/130/18-19 | Chala Social Hall | Complete | 2018-2019 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Construction Of Social Hall |  |  | Chala | -3.2989 | 37.7349 |  | County Government |  |  | Chala | Admin 3
006/132/131/18-19 | Chumvini 4 Door Toilet | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Door Toilet |  |  | Chala | -3.2113 | 37.7135 |  | County Government |  |  | Chala | Admin 3
006/132/132/18-19 | Mahandakini Ecde | Complete | 2018-2019 | Ketusha Constructions | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1239700 | 100 | 100 | Construction Of Class |  |  | Chala | -3.2456 | 37.73 |  | County Government |  |  | Chala | Admin 3
006/132/133/18-19 | Njukini Abc Rd | Complete | 2018-2019 | Njamrit Enterprises | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Grading & Gravelling Abc Rd |  |  | Chala | -3.1957 | 37.7123 |  | County Government |  |  | Chala | Admin 3
006/132/134/18-19 | Mahandakini Disp. Rd | Complete | 2018-2019 | Market View Investments | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.2452 | 37.7295 |  | County Government |  |  | Chala | Admin 3
006/132/135/18-19 | Mahandakini Disp. Twin Staff Hse | Complete | 2018-2019 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Disp Twin Staff Hse |  |  | Chala | -3.2468 | 37.7279 |  | County Government |  |  | Chala | Admin 3
006/132/136/18-19 | Chumvini Mkt Shed | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Mkt Shed |  |  | Chala | -3.2087 | 37.7125 |  | County Government |  |  | Chala | Admin 3
006/132/137/18-19 | Machungwani Kwa Hassan Rd | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.2559 | 37.7462 |  | County Government |  |  | Chala | Admin 3
006/132/138/18-19 | Njukini Shed &Toilet | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Shed Toilet |  |  | Chala | -3.1873 | 37.7246 |  | County Government |  |  | Chala | Admin 3
006/132/139/18-19 | Timboni Kwa Edward Road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2979579 | 100 | 100 | Murumming Of The Road |  |  | Mahoo | 3.349 | 37.703 |  | County Government |  |  | Mahoo | Admin 3
006/132/140/18-19 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/141/18-19 | Construction Of Lessesia Ecde Toilet | Complete | 2018-2019 | Jz Building& Construction Co. Ltd | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 499693.2 | 100 | 100 | Construction Of Toilet |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/142/18-19 | Msengoni Road Opening | Complete | 2018-2019 | Niko Genral Agencies | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1958752.8 | 100 | 100 | Road Formation |  |  | Mahoo | 3.3939 | 37.7121 |  | County Government |  |  | Mahoo | Admin 3
006/132/143/18-19 | Ngelesani Makloriti Road | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1910052 | 100 | 100 | Murruming Of The Road |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/144/18-19 | Langata Bypass Barrier Constructionroad | Complete | 2018-2019 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1632120 | 100 | 100 | Murrummung Road |  |  | Mahoo | 3.3742 | 37.6823 |  | County Government |  |  | Mahoo | Admin 3
006/132/145/18-19 | Nakuruto Ecde | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Ecde |  |  | Mahoo | 3.3378 | 37.7143 |  | County Government |  |  | Mahoo | Admin 3
006/132/146/18-19 | Renovation Works Of Mahandakini Dispensary | Complete | 2018-2019 | Borbada Enterprises, P.O Box 12444-80117 Mtopanga | 0 | Health Services | County Government | [7 empty] | 2497500 | 100 | 100 | Construction |  |  | Mahoo |  |  |  | County Government |  |  | Mahoo | Admin 3
006/132/147/18-19 | Mahoo Ecde Kitchen | Complete | 2018-2019 | Makena General Stores | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1258588.4 | 100 | 100 | Construction Of Kitchen |  |  | Mahoo | 3.473 | 38.5849 |  | County Government |  |  | Mahoo | Admin 3
006/132/148/18-19 | Kirimeri Nursery Perimeter Fence | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ecde |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/149/18-19 | Supply Of Fertilizer | Complete | 2018-2019 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Supply Of Fertilizer |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/150/18-19 | Fencing Of Orkung'U Pre-School | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Fencing Construction |  |  | Mata | -3.5057 | 37.6865 |  | County Government |  |  | Mata | Admin 3
006/132/151/18-19 | Construction Of 1 Classroom Kasaani Pre-School | Ongoing | 2018-2019 | Tahary Enterprises | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1354584.2 | 100 | 100 | Completion Of Kasaani Ecde Phase 2 |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/152/18-19 | Construction Of Kasaani Ecde Classroom 2 | Complete | 2018-2019 | Tahary Enterprises | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Completion Of Kasaani Ecde Phase 2 |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/153/18-19 | Kachero Ecd 2 Classrooms | Ongoing | 2018-2019 | Tahary Enterprises | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 2610882.6 | 100 | 100 | Construction Of Kachero Ecde 2 Classrooms Phase 2 |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/154/18-19 | Grogan Ecd 2 Classrooms | Ongoing | 2018-2019 | Kiwalwa Kwetu Ltd | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1764049.12 | 100 | 100 | Completion Of Gregan Ecde Classroom Phase 2 |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/155/18-19 | Ndilindau Ecd Chairs |  | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ndilindau Ecd Chairs |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/156/18-19 | Construction Of 1 Classroom - Orkung Pre School | Complete | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.5156 | 37.7705 |  | County Government |  |  | Mata | Admin 3
006/132/157/18-19 | Construction Of Mata Youth Polytechnic | Stalled | 2018-2019 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Mata Vtc |  |  | Mata | -3.3906 | 37.5853 |  | County Government |  |  | Mata | Admin 3
006/132/158/18-19 | Construction Of Kachero Dispensary | Complete | 2018-2019 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of The Dispensary |  |  | Mata | -3.5579 | 37.7323 |  | County Government |  |  | Mata | Admin 3
006/132/159/18-19 | Fencing Of Mata Dispensary | Complete | 2018-2019 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Fencing Of Mata Dispensary |  |  | Mata | -3.3713 | 37.7055 |  | County Government |  |  | Mata | Admin 3
006/132/160/18-19 | Equipping Of Ndilidau Dispensary | Complete | 2018-2019 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Supply Of Equipment At Ndilidau Dispensary |  |  | Mata | -3.3802 | 37.7489 |  | County Government |  |  | Mata | Admin 3
006/132/161/18-19 | Formation Of King'Wareni - Kimondia - Rekeke Road | Complete | 2018-2019 | Market View Investments | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | New Road Formation |  |  | Mata | -3.4647 | 37.7175 |  | County Government |  |  | Mata | Admin 3
006/132/162/18-19 | Culverts Installation At King'Wareni - Kimondia - Rekeke Road | Complete | 2018-2019 | Market View Investments | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 2103834 | 100 | 100 | Culverts Installation |  |  | Mata | -3.4217 | 37.5674 |  | County Government |  |  | Mata | Admin 3
006/132/163/18-19 | Murraming, Culvert & Drainage Culvert Mkuyuni - King'Wareni Road | Complete | 2018-2019 | Spartacus K Ltd | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [7 empty] | 1997520 | 100 | 100 | Culverts Installation |  |  | Mata | -3.3766 | 37.6601 |  | County Government |  |  | Mata | Admin 3
006/132/164/17-18 | Phase 2 Fencing Of Chala Dispensary | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [7 empty] | 994945 | 100 | 100 | Construction Of Disp Fence |  |  | Chala | -3.2955 | 37.7357 |  | County Government |  |  | Chala | Admin 3
006/132/165/17-18 | Chala Disp. Staff House Renovation | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Renovation Of Disp Staff House |  |  | Chala | -3.2955 | 37.7357 |  | County Government |  |  | Chala | Admin 3
006/132/166/17-18 | Chala Ecde | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Class |  |  | Chala | -3.2951 | 37.7361 |  | County Government |  |  | Chala | Admin 3
006/132/167/17-18 | Njukini Bodaboda Shed | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Bodaboda Shed |  |  | Chala | -3.1883 | 37.7245 |  | County Government |  |  | Chala | Admin 3
006/132/168/17-18 | Kindongu Box Culvert | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Culvert |  |  | Chala | -3.3344 | 37.7359 |  | County Government |  |  | Chala | Admin 3
006/132/169/17-18 | Chala Disp. Fence | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Disp Fence |  |  | Chala | -3.2955 | 37.7357 |  | County Government |  |  | Chala | Admin 3
006/132/170/17-18 | Chala Vtc Fence | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Fencing Vtc |  |  | Chala | -3.2978 | 37.7308 |  | County Government |  |  | Chala | Admin 3
006/132/171/17-18 | Mahandakini Disp. Twin Staff Hse | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Disp Twin Staff Hse |  |  | Chala | -3.2468 | 37.7279 |  | County Government |  |  | Chala | Admin 3
006/132/172/17-18 | Chumvini Mkt Shed | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Mkt Shed |  |  | Chala | -3.2087 | 37.7125 |  | County Government |  |  | Chala | Admin 3
006/132/173/17-18 | Machungwani Kwa Hassan Rd | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.2559 | 37.7462 |  | County Government |  |  | Chala | Admin 3
006/132/174/17-18 | Lumi Dispensary | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Dispensary |  |  | Chala | -3.1978 | 37.7543 |  | County Government |  |  | Chala | Admin 3
006/132/175/17-18 | Njukini Shed &Toilet | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Shed Toilet |  |  | Chala | -3.1873 | 37.7246 |  | County Government |  |  | Chala | Admin 3
006/132/176/17-18 | Rehabilitation Of Remus-Maroro Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3827 | 37.6868 |  | County Government |  |  | Mahoo | Admin 3
006/132/177/17-18 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/178/17-18 | Kirimeri Nursery Perimeter Fence | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ecde |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/179/17-18 | Msengoni Road Opening | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Road Formation |  |  | Mahoo | 3.3939 | 37.7121 |  | County Government |  |  | Mahoo | Admin 3
006/132/180/17-18 | Malkulority Ecde | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Class |  |  | Mahoo | 3.3494 | 37.7082 |  | County Government |  |  | Mahoo | Admin 3
006/132/181/17-18 | Youth Road California | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3792 | 37.673 |  | County Government |  |  | Mahoo | Admin 3
006/132/182/17-18 | Maintenance Of Langata-Bypass Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3829 | 37.6797 |  | County Government |  |  | Mahoo | Admin 3
006/132/183/17-18 | Miereni Community Social Hall | Complete | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Construction Of Social Hall |  |  | Mahoo | 3.3847 | 37.6879 |  | County Government |  |  | Mahoo | Admin 3
006/132/184/17-18 | Malkloriti B Ecde And 3 Door Toilet | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Ecde |  |  | Mahoo | 3.3695 | 37.692 |  | County Government |  |  | Mahoo | Admin 3
006/132/185/17-18 | Kirimeri Nursery Perimeter Fence | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ecde |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/186/17-18 | Fishing Washing Shade | Complete | 2017-2018 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Construction Of Fishing Washing Shade |  |  | Mata | -3.5279 | 37.6799 |  | County Government |  |  | Mata | Admin 3
006/132/187/17-18 | Kasahani Nursery | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1513995.2 | 100 | 100 | Construction Kasahani Nursery |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/188/17-18 | Supply And Intallation Of 10,000Ltrs Water Tank At Orkung Ecde | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Supply Of Water Storage Tank |  |  | Mata | -3.5157 | 37.7769 |  | County Government |  |  | Mata | Admin 3
006/132/189/17-18 | Fencing Of Orkung'U Pre-School | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Fencing Construction |  |  | Mata | -3.5057 | 37.6865 |  | County Government |  |  | Mata | Admin 3
006/132/190/17-18 | Construction Of 2 Classrooms Kasaani Pre-School | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1192155 | 100 | 100 | Construction Of 2 Classrooms Kasaani |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/191/17-18 | Construction Of A Kitchen - Orkung'U Pre-School | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of A Kitchen |  |  | Mata | -3.3719 | 37.7146 |  | County Government |  |  | Mata | Admin 3
006/132/192/17-18 | Construction Of Kachero Ecde | Ongoing | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1195414.8 | 100 | 100 | Construction Of Kachero Ecde |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/193/17-18 | Construction Of Grogan Ecde | Stalled | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [7 empty] | 1069348 | 100 | 100 | Construction Of Classroom |  |  | Mata | -3.4768 | 37.6864 |  | County Government |  |  | Mata | Admin 3
006/132/194/17-18 | Mata Pre School Construction Of 1 Classroom | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Mata Pre School |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/195/17-18 | Construction Of Mata Youth Polytechnic |  | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Mata Vtc |  |  | Mata | -3.3906 | 37.5853 |  | County Government |  |  | Mata | Admin 3
006/132/196/17-18 | Fencing Of Mata Dispensary | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [7 empty] | 499380 | 100 | 100 | Fencing Of Mata Dispensary |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/197/17-18 | Equiping Of Ndilindau Dispensary | Complete | 2017-2018 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Supply Of Equipment At Ndilidau Dispensary |  |  | Mata | -3.3802 | 37.7489 |  | County Government |  |  | Mata | Admin 3
006/132/198/17-18 | Empowering Tkfc |  | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 |  |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/199/17-18 | Construction Of Bridges, Drifts & Culverts Installation | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Bridges,Drifts &Culverts Installation |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/200/17-18 | Kimondia Road Upgrading | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Road Formation |  |  | Mata | -3.4369 | 37.7298 |  | County Government |  |  | Mata | Admin 3
006/132/201/17-18 | Maintenance Of Mukuyuni-Kimwareni-Kimondia Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading Of Mkuyuni Rekeke Road |  |  | Mata | -3.3719 | 37.7146 |  | County Government |  |  | Mata | Admin 3
006/132/202/17-18 | Jipe Road Bridges | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Fixing Of Culverts |  |  | Mata | -3.5166 | 37.7708 |  | County Government |  |  | Mata | Admin 3
006/132/203/17-18 | Culverts Installation-Mata-Njoro-Mtaa Kuja- Rmlf | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Culvert Installation At Mata-Njoro- Mtakuja Road |  |  | Mata | -3.3906 | 37.5853 |  | County Government |  |  | Mata | Admin 3
006/132/204/17-18 | Mata Roads Maintainance- Rmlf | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Mata Roads Maintainance- Rmlf |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/205/17-18 | Bodaboda Shed At Cess | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of The Bodaboda Shed |  |  | Mata | -3.5166 | 37.7708 |  | County Government |  |  | Mata | Admin 3
006/132/206/17-18 | Jipe Boat Harbour | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Jipe Boat Harbour |  |  | Mata | -3.4348 | 37.7006 |  | County Government |  |  | Mata | Admin 3
006/132/207/17-18 | Fertilizer For Farmers - Mboghoni | Stalled | 2017-2018 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Fertilizer For Farmers - Mboghoni |  |  | Mboghoni | -3.4309 | 37.7009 |  | County Government |  |  | Mboghoni | Admin 3
006/132/208/17-18 | Equipping Mboghonyi Ward Ecdee Centres | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Equipping Mboghonyi Ward Ecdee Centres |  |  | Mboghoni | -3.4764 | 37.708 |  | County Government |  |  | Mboghoni | Admin 3
006/132/209/17-18 | Equipping Of Kambughu Youth Polytechnic | Complete | 2017-2018 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Equipping Of Kambughu Youth Polytechnic |  |  | Mboghoni | -3.436 | 37.6158 |  | County Government |  |  | Mboghoni | Admin 3
006/132/210/17-18 | Murraming Of Python Hill Village Road With 2 Lines 900 Mm Culverts | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Python Hill Village Road With 2 Lines 900 Mm Culverts |  |  | Mboghoni | -3.4766 | 37.6688 |  | County Government |  |  | Mboghoni | Admin 3
006/132/211/17-18 | Murraming Of Abori-Lambo Road | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Abori-Lambo Road |  |  | Mbhoghoni | -3.4594 | 37.6953 |  | County Government |  |  | Mbhoghoni | Admin 3
006/132/212/17-18 | Kimorigo Kilabuni Msengoni Road Upgrading | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Kimorigo Kilabuni Msengoni Road Upgrading |  |  | Mboghoni | -3.4604 | 37.692 |  | County Government |  |  | Mboghoni | Admin 3
006/132/213/17-18 | Eldoro Kitoghoto Ngutuni Road Murraming And Lineof 900Mm Culverts | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Eldoro Kitoghoto Ngutuni Road Murraming And Lineof 900Mm Culverts |  |  | Mboghoni | -3.4763 | 37.6822 |  | County Government |  |  | Mboghoni | Admin 3
006/132/214/17-18 | Murraming Of Mrabani-Kambungu Road- Rmlf | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of Mrabani-Kambungu Road- Rmlf |  |  | Mboghoni | -3.436 | 37.616 |  | County Government |  |  | Mboghoni | Admin 3
006/132/215/17-18 | Murraming Eldoro-Kitoghoto-Ngutini Road- Rmlf | Complete | 2017-2018 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Eldoro-Kitoghoto-Ngutini Road- Rmlf |  |  | Mboghoni | -3.4763 | 37.6822 |  | County Government |  |  | Mboghoni | Admin 3
006/132/216/17-18 | Construction Of A Social Hall At Kiwalwa Village | Ongoing | 2017-2018 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Construction Of A Social Hall At Kiwalwa Village |  |  | Mboghoni | -3.4268 | 37.6887 |  | County Government |  |  | Mboghoni | Admin 3
006/132/217/16-17 | Chala Disp. Staff House | Complete | 2016-2017 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Disp Staff House |  |  | Chala | -3.2961 | 37.735 |  | County Government |  |  | Chala | Admin 3
006/132/218/16-17 | Njukini Mkt Grading & Gravelling | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading & Gravelling Njukini Mkt |  |  | Chala | -3.1874 | 37.7216 |  | County Government |  |  | Chala | Admin 3
006/132/219/16-17 | Chala Chini Ph 2 | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.3113 | 37.7281 |  | County Government |  |  | Chala | Admin 3
006/132/220/16-17 | Chala Chini Rd | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.3342 | 37.7354 |  | County Government |  |  | Chala | Admin 3
006/132/221/16-17 | Chala Secondary Rd | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.2882 | 37.7385 |  | County Government |  |  | Chala | Admin 3
006/132/222/16-17 | Bishop Njenga Rd | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Grading Of The Road |  |  | Chala | -3.2053 | 37.7153 |  | County Government |  |  | Chala | Admin 3
006/132/223/16-17 | Njukini Shed &Toilet | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Shed Toilet |  |  | Chala | -3.1873 | 37.7246 |  | County Government |  |  | Chala | Admin 3
006/132/224/16-17 | Rehabilitation Of Remus-Maroro Road | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3827 | 37.6868 |  | County Government |  |  | Mahoo | Admin 3
006/132/225/16-17 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/226/16-17 | Kirimeri Nursery Perimeter Fence | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Ecde |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/227/16-17 | Kimondia, Matutani And Kitivo/Ngwakwele Land Reclamation For Growing Maize,Rice,Mangoes,Bananas. | Complete | 2016-2017 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Desilting Canals |  |  | Mata | -3.4474 | 37.7175 |  | County Government |  |  | Mata | Admin 3
006/132/228/16-17 | Hormone Syncronization Programme For Livestock In Orkungu Salaita Njoro | Complete | 2016-2017 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Hormone Synchronization Programme |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/229/16-17 | Construction Of Crush Pens (Kimala And Njoro) (Mata Ward)- | Complete | 2016-2017 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Construction Of Crush Pens |  |  | Mata | -3.4669 | 37.5434 |  | County Government |  |  | Mata | Admin 3
006/132/230/16-17 | Starting Of Fishponds In Lake Jipe | Complete | 2016-2017 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Construction Of The Fish Ponds |  |  | Mata | -3.5266 | 37.5658 |  | County Government |  |  | Mata | Admin 3
006/132/231/16-17 | Construction Of 1 Classroom-Kimondia Pre School | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.4374 | 37.6853 |  | County Government |  |  | Mata | Admin 3
006/132/232/16-17 | Fencing Of Orkung'U Pre-School | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Fencing Construction |  |  | Mata | -3.5057 | 37.6865 |  | County Government |  |  | Mata | Admin 3
006/132/233/16-17 | Construction Of 1 Classroom Kasaani Pre-School | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.3802 | 37.7489 |  | County Government |  |  | Mata | Admin 3
006/132/234/16-17 | Construction Of A Kitchen - Orkung'U Pre-School | Complete | 2016-2017 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of A Kitchen |  |  | Mata | -3.3719 | 37.7146 |  | County Government |  |  | Mata | Admin 3
006/132/235/16-17 | Construction Of Mata Youth Polytechnic | Complete | 2016-2017 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Construction Of Mata Vtc |  |  | Mata | -3.3906 | 37.5853 |  | County Government |  |  | Mata | Admin 3
006/132/236/16-17 | Jipe Road Bridges | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Fixing Of Culverts |  |  | Mata | -3.5166 | 37.7708 |  | County Government |  |  | Mata | Admin 3
006/132/237/16-17 | Rehabilation Of Njoro-Mboghoni Road (12Km) - Pending Bills | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Rehabilation Of Njoro-Mboghoni Road (12Km) - Pending Bills |  |  | Mboghoni | -3.4871 | 37.6903 |  | County Government |  |  | Mboghoni | Admin 3
006/132/238/16-17 | Eldoro Kitoghoto Ngutuni Road Murraming And Lineof 900Mm Culverts | Complete | 2016-2017 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Eldoro Kitoghoto Ngutuni Road Murraming And Lineof 900Mm Culverts |  |  | Mboghoni | -3.4704 | 37.6688 |  | County Government |  |  | Mboghoni | Admin 3
006/132/239/15-16 | Njukini Mkt Grading & Gravelling | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading & Gravelling Njukini Mkt |  |  | Chala | -3.1874 | 37.7216 |  | County Government |  |  | Chala | Admin 3
006/132/240/15-16 | Bishop Njenga Rd | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Grading Of The Road |  |  | Chala | -3.2053 | 37.7153 |  | County Government |  |  | Chala | Admin 3
006/132/241/15-16 | Chala Chini Tank 10000L | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Purchase Of Tank |  |  | Chala | -3.3164 | 37.7267 |  | County Government |  |  | Chala | Admin 3
006/132/242/15-16 | Irrigation Two 10000L Tanks | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Purchase Of Two L Tanks |  |  | Chala | -3.2133 | 37.7518 |  | County Government |  |  | Chala | Admin 3
006/132/243/15-16 | Mahandakini Disp. Twin Staff Hse | Complete | 2015-2016 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Disp Twin Staff Hse |  |  | Chala | -3.2468 | 37.7279 |  | County Government |  |  | Chala | Admin 3
006/132/244/15-16 | Kivukoni 10 Door Pit Latrine | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Door Pit Latrine |  |  | Chala | -3.2625 | 37.7467 |  | County Government |  |  | Chala | Admin 3
006/132/245/15-16 | Chumvini Mkt Shed | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Mkt Shed |  |  | Chala | -3.2087 | 37.7125 |  | County Government |  |  | Chala | Admin 3
006/132/246/15-16 | Machungwani Kwa Hassan Rd | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Grading And Gravelling |  |  | Chala | -3.2559 | 37.7462 |  | County Government |  |  | Chala | Admin 3
006/132/247/15-16 | Timboni Kwa Edward Road | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murumming Of The Road |  |  | Mahoo | 3.349 | 37.703 |  | County Government |  |  | Mahoo | Admin 3
006/132/248/15-16 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/249/15-16 | Timboni Kwa Edward Road | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murumming Of The Road |  |  | Mahoo | 3.349 | 37.703 |  | County Government |  |  | Mahoo | Admin 3
006/132/250/15-16 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/251/15-16 | Trench Digging And Pipe Installation At Kitivo Farms - Mata Ward (Pending Bills) | Complete | 2015-2016 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Rehabilitation Of Kitivo Farms |  |  | Mata | -3.3714 | 37.439 |  | County Government |  |  | Mata | Admin 3
006/132/252/15-16 | Construction Of Crush Pens (Kimala And Njoro) (Mata Ward)- | Complete | 2015-2016 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Construction Of Crush Pens |  |  | Mata | -3.4669 | 37.5434 |  | County Government |  |  | Mata | Admin 3
006/132/253/15-16 | Starting Of Fishponds In Lake Jipe | Complete | 2015-2016 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Construction Of The Fish Ponds |  |  | Mata | -3.5266 | 37.5658 |  | County Government |  |  | Mata | Admin 3
006/132/254/15-16 | Mata Pre School Construction Of 1 Classroom | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Mata Pre School Construction Of 1 Classroom |  |  | Mata | -3.4479 | 37.7556 |  | County Government |  |  | Mata | Admin 3
006/132/255/15-16 | Construction Of 1 Classroom - Rekeke Pre School | Complete | 2015-2016 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom - Rekeke Pre School |  |  | Mata | -3.4479 | 37.7556 |  | County Government |  |  | Mata | Admin 3
006/132/256/15-16 | Construction Of Kachero Dispensary | Complete | 2015-2016 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Kachero Dispensary |  |  | Mata | -3.5069 | 37.6574 |  | County Government |  |  | Mata | Admin 3
006/132/257/15-16 | Jipe Road Bridges | Complete | 2015-2016 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Jipe Road Bridges |  |  | Mata | -3.5166 | 37.7708 |  | County Government |  |  | Mata | Admin 3
006/132/258/14-15 | Lumi Dispensary | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Dispensary |  |  | Chala | -3.1978 | 37.7543 |  | County Government |  |  | Chala | Admin 3
006/132/259/14-15 | Mandakini Maternity Block& Renovation | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Maternity Block& Renovation |  |  | Chala | -3.2468 | 37.7279 |  | County Government |  |  | Chala | Admin 3
006/132/260/14-15 | Njukini Shed &Toilet | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Shed Toilet |  |  | Chala | -3.1873 | 37.7246 |  | County Government |  |  | Chala | Admin 3
006/132/261/14-15 | Chumvini Twin Workshop & Toilet | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Construction Of Twin Workshop & Toilet |  |  | Chala | -3.2083 | 37.7167 |  | County Government |  |  | Chala | Admin 3
006/132/262/14-15 | Rehabilitation Harambee/Chakaleri Timbila Rd | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3838 | 37.7153 |  | County Government |  |  | Mahoo | Admin 3
006/132/263/14-15 | Rehabilitation Of Remus-Maroro Road | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3827 | 37.6868 |  | County Government |  |  | Mahoo | Admin 3
006/132/264/14-15 | Rehabilitation Of Darajani Shopping Centre | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3893 | 37.7055 |  | County Government |  |  | Mahoo | Admin 3
006/132/265/14-15 | Majengo,Russiain Bomani | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3955 | 37.6795 |  | County Government |  |  | Mahoo | Admin 3
006/132/266/14-15 | Leshampta Merosho Road | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murruming Of The Road |  |  | Mahoo | 3.3057 | 37.7208 |  | County Government |  |  | Mahoo | Admin 3
006/132/267/14-15 | Competion Of Majengo Road | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murrumming Of The Road |  |  | Mahoo | 3.3893 | 37.7055 |  | County Government |  |  | Mahoo | Admin 3
006/132/268/14-15 | Rehabilitation Of Luworo Road | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murumming Of The Road |  |  | Mahoo | 3.3893 | 37.7055 |  | County Government |  |  | Mahoo | Admin 3
006/132/269/14-15 | Rehabilitation Of Kimala Irrigation Scheme(Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Rehabilitation Of Canal |  |  | Mata | 3.3975 | 37.1779 |  | County Government |  |  | Mata | Admin 3
006/132/270/14-15 | Rehabilitation Of Kitivo Farms(Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Rehabilitation Of Canals |  |  | Mata | 3.6514 | 37.3126 |  | County Government |  |  | Mata | Admin 3
006/132/271/14-15 | Starting Of Mkocheni Kachero Irrigation Scheme(Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Rehabilitation Of Canals |  |  | Mata | 3.7564 | 37.2357 |  | County Government |  |  | Mata | Admin 3
006/132/272/14-15 | Construction Of Crush Pens (Kimala And Njoro) (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Construction Of Crush Pens |  |  | Mata | -3.4669 | 37.5434 |  | County Government |  |  | Mata | Admin 3
006/132/273/14-15 | Construction Of Sheds At Lake Jipe (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Construction Of 1 Shed At Lake Jipe Entrance |  |  | Mata | -3.5679 | 37.7671 |  | County Government |  |  | Mata | Admin 3
006/132/274/14-15 | Construction Of Fish Pond For Farmers (Mata Ward) (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Agriculture, Livestock, Irrigation, Cooperatives and Blue Economy | County Government | [8 empty] | 100 | 100 | Construction Of The Fish Ponds |  |  | Mata | -3.5179 | 37.2439 |  | County Government |  |  | Mata | Admin 3
006/132/275/14-15 | Construction Of 1 Classroom (Salaita Preschool) (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.3911 | 37.7721 |  | County Government |  |  | Mata | Admin 3
006/132/276/14-15 | Construction Of 1 Classroom (Orkungu Preschool) (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.5156 | 37.7705 |  | County Government |  |  | Mata | Admin 3
006/132/277/14-15 | Furnishing Of 6 Ecd Centers (Mata Ward) | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Furnishing Of 6 Ecd Centers (Mata Ward) |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/278/14-15 | Construction Of Mwangemi Ecd Toilet (Mata Ward) | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Toilet |  |  | Mata | -3.4182 | 37.7661 |  | County Government |  |  | Mata | Admin 3
006/132/279/14-15 | Constuction Of 1 Classroom (Mwangenyi Pre School) (Mata Ward) | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.3666 | 37.6744 |  | County Government |  |  | Mata | Admin 3
006/132/280/14-15 | Constuction Of 2 Classroom (Salaita Pre School) (Mata Ward) | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.3422 | 37.6432 |  | County Government |  |  | Mata | Admin 3
006/132/281/14-15 | Construction Of 1 Classroom (Tanjine Preschool) (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of 1 Classroom |  |  | Mata | -3.3943 | 37.5663 |  | County Government |  |  | Mata | Admin 3
006/132/282/14-15 | Construction Of Kachero Dispensary (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of The Main Dispensary Block |  |  | Mata | -3.5639 | 37.7702 |  | County Government |  |  | Mata | Admin 3
006/132/283/14-15 | Renovation Of Staff Houses - Mata Dispensary (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Renovation Of Staff Quarters |  |  | Mata | -3.3867 | 37.469 |  | County Government |  |  | Mata | Admin 3
006/132/284/14-15 | Rekeke Health Centre Construction Of Staff Houses (Mata Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of The Staff Quarters |  |  | Mata | -3.4087 | 37.7144 |  | County Government |  |  | Mata | Admin 3
006/132/285/14-15 | Refurbishment Of Lotima Ecd(Mboghoni Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Renovation Of The Class Room |  |  | Mboghoni | -3.457 | 37.691 |  | County Government |  |  | Mboghoni | Admin 3
006/132/286/14-15 | Construction Of Python Hill Ecd(Mboghoni Ward) | Complete | 2014-2015 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Construction Of Ecde Classroom |  |  | Mboghoni | -3.4641 | 37.6311 |  | County Government |  |  | Mboghoni | Admin 3
006/132/287/14-15 | Completion Of Kitobo Dispensary(Mboghoni Ward)-Wdf | Ongoing | 2014-2015 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Renovation,Construction And Upgraing Of The Dispensary |  |  | Mboghoni | -3.4413 | 37.6053 |  | County Government |  |  | Mboghoni | Admin 3
006/132/288/14-15 | Maternity Wing-Kiwalwa Dispensary(Mboghoni Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/289/14-15 | Construction Of Culverts(Kitobo-Mboghoni Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  | 37.701 |  | County Government |  |  | Mboghoni | Admin 3
006/132/290/14-15 | Construction Of Kimondia Road-(Mboghoni Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Clearing And Expansion Of The Road |  |  | Mboghoni | -3.4306 | 37.701 |  | County Government |  |  | Mboghoni | Admin 3
006/132/291/14-15 | Kimorigo Drains | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Clearing Of The Drains |  |  | Mboghoni | -3.457 | 37.691 |  | County Government |  |  | Mboghoni | Admin 3
006/132/292/14-15 | Murraming Of Mrabai Makine Edora Road(Mboghonyi Ward) | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/293/14-15 | Upgrading Of Ngutuni Kitoghoto Eldoro Road(Mboghoni Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Murraming Of The Road |  |  | Mboghoni | -3.4763 | 37.6822 |  | County Government |  |  | Mboghoni | Admin 3
006/132/294/14-15 | Upgrading Of Mboghoni Mereni Road(Mboghoni Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/295/14-15 | Ngutuni Town Road(Mboghoni Ward)-Wdf | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/296/14-15 | Pending Bills - Mboghoni Ward | Complete | 2014-2015 | n/a | 0 |  | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/297/14-15 | Purchase Of Fencing Material -Kitobo ,Mboghoni (Rebudgeted) | Complete | 2014-2015 | n/a | 0 |  | County Government | [8 empty] | 100 | 100 |  |  |  | Mboghoni |  |  |  | County Government |  |  | Mboghoni | Admin 3
006/132/298/14-15 | Murraming Of Eldoro Mokine Road | Complete | 2014-2015 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Upgraiding Of The Road |  |  | Mboghoni | -3.474 | 37.631 |  | County Government |  |  | Mboghoni | Admin 3
006/132/299/13-14 | Bishop Njenga Fence | Complete | 2013-2014 | n/a | 0 | Education, Libraries and VTCs | County Government | [8 empty] | 100 | 100 | Compound Fencing |  |  | Chala | -3.2053 | 37.7153 |  | County Government |  |  | Chala | Admin 3
006/132/300/13-14 | Purchase Of Dispensary Drugs | Complete | 2013-2014 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Supply Of Medical Drugs |  |  | Mata | -3.4748 | 37.7562 |  | County Government |  |  | Mata | Admin 3
006/132/301/13-14 | Construction Of A Dispensary | Complete | 2013-2014 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Construction Of Foundation Floor |  |  | Mata | -3.5617 | 37.77 |  | County Government |  |  | Mata | Admin 3
006/132/302/13-14 | Purchase Of Dispensary Furniture | Complete | 2013-2014 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Equipping Of Furniture |  |  | Mata | -3.4276 | 37.7335 |  | County Government |  |  | Mata | Admin 3
006/132/303/13-14 | Purchase of Marternity Beds | Complete | 2013-2014 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Purchase of Marternity Beds |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/304/13-14 | Purcahse of Inpatient ward beds | Complete | 2013-2014 | n/a | 0 | Health Services | County Government | [8 empty] | 100 | 100 | Purcahse of Inpatient ward beds |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/305/13-14 | Culvet Installation | Complete | 2013-2014 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Culvet Installation |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/306/13-14 | Construction of community Hall | Complete | 2013-2014 | n/a | 0 | Youth, Sports, Gender and Social Services | County Government | [8 empty] | 100 | 100 | Construction of community Hall |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
006/132/307/13-14 | Purchase of Fencing Material -KITOBO ,MBOGHONI | Complete | 2013-2014 | n/a | 0 | Public Works, Housing, Roads, Transport, Energy and Infrastructure | County Government | [8 empty] | 100 | 100 | Purchase of Fencing Material -KITOBO ,MBOGHONI |  |  | Mata |  |  |  | County Government |  |  | Mata | Admin 3
County Government